## BenchMark
ABDA
ID | Hierachy levels
ID | Level 1 | Level 2 | Level 3 | Level 4 | B1 | B2 | B3 | B4 | B5 | B6
Total
A | Delivery Plan | 0 | 0 | 0
A.1 | Detailed WBS with schedule and S-curve | 0 | 0 | 0
A.1.1 | Detailed WBS with schedule and S-curve | 0 | 0 | Bidder to follow the WBS defined in ER
A.1.2 | Detailed WBS with schedule and S-curve | 0 | 0 | Sufficiency and completeness of the WBS
A.1.3 | Detailed WBS with schedule and S-curve | 0 | 0 | Schedule is given in required format
A.1.4 | Detailed WBS with schedule and S-curve | 0 | 0 | Interim milestones
A.1.5 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of milestones
A.1.6 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of linkages
A.1.7 | Detailed WBS with schedule and S-curve | 0 | 0 | Consistency with delivery narrative and methodological approach
A.1.8 | Detailed WBS with schedule and S-curve | 0 | 0 | Critical path is highlighted in the schedule program
A.1.9 | Detailed WBS with schedule and S-curve | 0 | 0 | Resources allocation
A.1.10 | Detailed WBS with schedule and S-curve | 0 | 0 | S-curve is probably drawn in the schedule program
A.2 | Delivery Narrative | 0 | 0 | 0
A.2.1 | Delivery Narrative | 0 | 0 | Understanding of the works
A.2.2 | Delivery Narrative | 0 | 0 | Well written and demonstration of approach and delivery of the project
A.2.3 | Delivery Narrative | 0 | 0 | Key activities and deliverables
A.2.4 | Delivery Narrative | 0 | 0 | Feasibility of the approach
A.2.5 | Delivery Narrative | 0 | 0 | Constraints involved with the approach
A.2.6 | Delivery Narrative | 0 | 0 | Resources allocation are persuative and feasible
A.2.7 | Delivery Narrative | 0 | 0 | Advantage of offerred contract strategy
A.2.8 | Delivery Narrative | 0 | 0 | Linkage to deliverable plan (above)
A.2.9 | Delivery Narrative | 0 | 0 | Added value to the Client
A.3 | Safety Plan | 0 | 0 | 0
A.3.1 | Safety Plan | 0 | 0 | Overall Safety Plan
A.3.2 | Safety Plan | 0 | 0 | Safety personnel
A.3.3 | Safety Plan | 0 | 0 | Safety plan for each WP, particularly for critical work items
A.3.4 | Safety Plan | 0 | 0 | Demonstration of historical records, data on safety of previous projects
A.3.5 | Safety Plan | 0 | 0 | Safety compliance to Client's requirement
A.3.6 | Safety Plan | 0 | 0 | Safety compliance to local authority
A.3.7 | Safety Plan | 0 | 0 | Evacuation and immediate actions to follow when safety incident occurs
A.4 | Risk Management Plan (including contingency plan) | 0 | 0 | 0
A.4.1 | Risk Management Plan (including contingency plan) | 0 | 0 | Overall risk management plan
A.4.2 | Risk Management Plan (including contingency plan) | 0 | 0 | Specific risk plan for critical work
A.4.3 | Risk Management Plan (including contingency plan) | 0 | 0 | Understanding risks, particularly during execution on critical items
A.4.4 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk assessment methodology
A.4.5 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk management register and tool
A.4.6 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk removal, reduction, and mitigation plan
A.4.7 | Risk Management Plan (including contingency plan) | 0 | 0 | Feasibility of the overal risk plan
A.5 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | 0
A.5.1 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Completeness of deliverables in tabular format
A.5.2 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Linkage of deliverables to detailed schedule
A.5.3 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Feasibility of the deliverable plan
B | Design | 0 | 0 | 0
B.1 | 0 | M&E | 0 | 0
B.1.1 | Design | M&E | General | QA/QC
B.1.2 | Design | M&E | General | Deliverable Plan
B.1.3 | Design | M&E | General | Value Engineering
B.1.4 | Design | M&E | General | Resource Plan
B.1.5 | Design | M&E | General | Risk and safety in design
B.1.6 | Design | M&E | Intake Chamber | Feasibility
B.1.7 | Design | M&E | Intake Chamber | Constructability
B.1.8 | Design | M&E | Intake Chamber | Correctness
B.1.9 | Design | M&E | Outside Intake Chamber | Feasibility
B.1.10 | Design | M&E | Outside Intake Chamber | Constructability
B.1.11 | Design | M&E | Outside Intake Chamber | Correctness
B.2 | 0 | Automation and Instrumentation (A&I) | 0 | 0
B.2.1 | Design | Automation and Instrumentation (A&I) | General | QA/QC | [5 empty] | 3
B.2.2 | Design | Automation and Instrumentation (A&I) | General | Deliverable Plan
B.2.3 | Design | Automation and Instrumentation (A&I) | General | Value Engineering
B.2.4 | Design | Automation and Instrumentation (A&I) | General | Resource Plan
B.2.5 | Design | Automation and Instrumentation (A&I) | General | Risk and safety in design
B.2.6 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Feasibility
B.2.7 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Constructability
B.2.8 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Correctness
B.2.9 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Feasibility
B.2.10 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Constructability
B.2.11 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Correctness
B.3 | 0 | Hydraulics and others | 0 | 0
B.3.1 | Design | Hydraulics and others | General | QA/QC
B.3.2 | Design | Hydraulics and others | General | Deliverable Plan
B.3.3 | Design | Hydraulics and others | General | Value Engineering
B.3.4 | Design | Hydraulics and others | General | Resource Plan
B.3.5 | Design | Hydraulics and others | General | Risk and safety in design
B.3.6 | Design | Hydraulics and others | Intake Chamber | Feasibility
B.3.7 | Design | Hydraulics and others | Intake Chamber | Constructability
B.3.8 | Design | Hydraulics and others | Intake Chamber | Correctness
B.3.9 | Design | Hydraulics and others | Outside Intake Chamber | Feasibility
B.3.10 | Design | Hydraulics and others | Outside Intake Chamber | Constructability
B.3.11 | Design | Hydraulics and others | Outside Intake Chamber | Correctness
B.4 | 0 | Civil/structural design | 0 | 0
B.4.1 | Design | Civil/structural design | General | QA/QC | 4 | 2
B.4.2 | Design | 0 | General | Deliverable Plan | 4
B.4.3 | Design | 0 | General | Value Engineering
B.4.4 | Design | 0 | General | Resource Plan | 4
B.4.5 | Design | 0 | General | Risk and safety in design | 3 | 4
B.4.6 | Design | 0 | Intake Chamber | Feasibility | 4
B.4.7 | Design | 0 | Intake Chamber | Constructability
B.4.8 | Design | 0 | Intake Chamber | Correctness | 4 | 2
B.4.9 | Design | 0 | Outside Intake Chamber | Feasibility | 4 | 0
B.4.10 | Design | 0 | Outside Intake Chamber | Constructability |  | 0
B.4.11 | Design | 0 | Outside Intake Chamber | Correctness |  | 0
C | Construction/Installation Program and methodology | 0 | 0 | 0
C.1 | 0 | Control System, Automation & Instrumentation | 0 | 0
C.1.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.1.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.1.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.1.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.1.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.2 | 0 | Main Mechanical Works | 0 | 0
C.2.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.2.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.2.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.2.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.2.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.3 | 0 | Main Electrical Works | 0 | 0
C.3.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.3.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.3.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.3.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.3.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.4 | 0 | Piping | 0 | 0
C.4.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.4.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.4.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.4.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.4.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.5 | 0 | Other civil Structure | 0 | 0
C.5.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.5.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.5.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.5.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.5.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
D | Procurement and Installation of long-lead equipment and major process items | Procurement and Installation of long-lead equipment and major process items | 0 | 0
D.1 | 0 | Procurement plan and list of sub-work packages | 0 | 0
D.1.1 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Details of proposed procurement plan
D.1.2 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Supplier detail
D.1.3 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Installation and testing
D.1.4 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Warantty and defect liability
D.1.5 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Feasibility of procurement methodology
D.1.6 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Added value to the Client
D.2 | 0 | Delivery, storage, logistics and materials management plan. | 0 | 0
D.2.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Storage plan on site
D.2.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Losgistic plan
D.3 | 0 | Equipment list | 0 | 0
D.3.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Testing schedule
D.3.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | FAT
D.3.3 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Feasibility of installation method
D.4 | 0 | Service support | 0 | 0
D.4.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Availability of local service support
D.4.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Responsibility of local service support
E | Capacity (Personal & Resources) | Capacity (Personal & Resources) | 0 | 0
E.1 | 0 | Organizational chart | 0 | 0
E.1.1 | Capacity (Personal & Resources) |  | 0 | Overal organization chart | 2 | 4 | 5 | 1 | 5 | 5
E.1.2 | Capacity (Personal & Resources) |  | 0 | Functional linkage of the chart | 3 | 5 | 5 | 2 | 4 | 5
E.2 | 0 | Key team members | 0 | 0
E.2.1 | Capacity (Personal & Resources) | PM | 0 | Availability and commitment | 3 | 4 | 3 | 3 | 4 | 4
E.2.2 | Capacity (Personal & Resources) | PM | 15 | Total Experience (15 years) | 4 | 4 | 5 | 4 | 1 | 5
E.2.3 | Capacity (Personal & Resources) | PM | 10 | Similar experience (10 years) | 4 | 2 | 4 | 4 | 2 | 5
E.2.4 | Capacity (Personal & Resources) | Project Controller | 0 | Availability and commitment | 1 | 3 | 4 | 3 | 4 | 3
E.2.5 | Capacity (Personal & Resources) | Project Controller | 10 | Total Experience of the PM (10 years) | 3 | 3 | 4 | 5 | 3 | 4
E.2.6 | Capacity (Personal & Resources) | Project Controller | 5 | Similar experience of the PM (5 years) | 4 | 2 | 1 | 5 | 1 | 5
E.2.7 | Capacity (Personal & Resources) | Safety Manager | 0 | Availability and commitment | 4 | 3 | 3 | 2 | 4 | 3
E.2.8 | Capacity (Personal & Resources) | Safety Manager | 5 | Total Experience of the PM (10 years) | 4 | 4 | 4 | 4 | 5 | 5
E.2.9 | Capacity (Personal & Resources) | Safety Manager | 3 | Similar experience of the PM (5 years) | 4 | 2 | 3 | 5 | 2 | 5
E.2.10 | Capacity (Personal & Resources) | Contract Administrator | 0 | Availability and commitment | 1 | 4 | 4 | 4 | 4 | 3
E.2.11 | Capacity (Personal & Resources) | Contract Administrator | 10 | Total experience | 3 | 2 | 4 | 5 | 4 | 5
E.2.12 | Capacity (Personal & Resources) | Contract Administrator | 5 | Similar experience | 4 | 0 | 3 | 4 | 3 | 5
E.2.13 | Capacity (Personal & Resources) | Admin assistant Staff | 0 | Availability and commitment | 3 | 4 | 4 | 3 | 4 | 4
E.2.14 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Total experience | 3 | 4 | 4 | 5 | 4 | 5
E.2.15 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Similar experience | 1 | 0 | 4 | 5 | 3 | 4
E.2.16 | Capacity (Personal & Resources) | Quality manager | 0 | Availability and commitment | 4 | 3 | 3 | 5 | 3 | 3
E.2.17 | Capacity (Personal & Resources) | Quality manager | 10 | Total experience | 4 | 4 | 5 | 5 | 3 | 5
E.2.18 | Capacity (Personal & Resources) | Quality manager | 5 | Similar experience | 2 | 0 | 5 | 2 | 4 | 5
E.2.19 | Capacity (Personal & Resources) | Design manager | 0 | Availability and commitment | 3 | 0 | 4 | 3 | 3 | 3
E.2.20 | Capacity (Personal & Resources) | Design manager | 10 | Total experience | 4 | 3 | 4 | 5 | 5 | 5
E.2.21 | Capacity (Personal & Resources) | Design manager | 5 | Similar experience | 3 | 4 | 3 | 4 | 5 | 5
E.2.22 | Capacity (Personal & Resources) | Licensed structural engineer | 0 | Availability and commitment | 1 | 0 | 3 | 1 | 3 | 2
E.2.23 | Capacity (Personal & Resources) | Licensed structural engineer | 10 | Total experience | 4 | 3 | 4 | 5 | 3 | 5
E.2.24 | Capacity (Personal & Resources) | Licensed structural engineer | 5 | Similar experience | 4 | 4 | 4 | 4 | 3 | 4
E.2.25 | Capacity (Personal & Resources) | Hydraulic engineer | 0 | Availability and commitment | 4 | 4 | 4 | 3 | 3 | 2
E.2.26 | Capacity (Personal & Resources) | Hydraulic engineer | 10 | Total experience | 4 | 4 | 5 | 5 | 3 | 5
E.2.27 | Capacity (Personal & Resources) | Hydraulic engineer | 5 | Similar experience | 4 | 4 | 5 | 4 | 4 | 5
E.2.28 | Capacity (Personal & Resources) | Licensed mech engineer | 0 | Availability and commitment | 2 | 3 | 5 | 2 | 1 | 2
E.2.29 | Capacity (Personal & Resources) | Licensed mech engineer | 10 | Total experience | 4 | 4 | 5 | 5 | 4 | 5
E.2.30 | Capacity (Personal & Resources) | Licensed mech engineer | 5 | Similar experience | 4 | 3 | 5 | 4 | 2 | 5
E.2.31 | Capacity (Personal & Resources) | Licensed elec engineer | 0 | Availability and commitment | 2 | 2 | 4 | 4 | 3 | 2
E.2.32 | Capacity (Personal & Resources) | Licensed elec engineer | 10 | Total experience | 4 | 4 | 4 | 4 | 3 | 5
E.2.33 | Capacity (Personal & Resources) | Licensed elec engineer | 5 | Similar experience | 3 | 4 | 3 | 4 | 3 | 5
E.2.34 | Capacity (Personal & Resources) | A&I engineer | 0 | Availability and commitment | 2 | 4 | 1 | 4 | 3 | 1
E.2.35 | Capacity (Personal & Resources) | A&I engineer | 10 | Total experience | 3 | 4 | 4 | 5 | 5 | 4
E.2.36 | Capacity (Personal & Resources) | A&I engineer | 5 | Similar experience | 1 | 4 | 4 | 5 | 4 | 3
E.2.37 | Capacity (Personal & Resources) | Construction Manager | 0 | Availability and commitment | 1 | 2 | 4 | 4 | 4 | 3
E.2.38 | Capacity (Personal & Resources) | Construction Manager | 10 | Total experience | 4 | 3 | 4 | 4 | 4 | 5
E.2.39 | Capacity (Personal & Resources) | Construction Manager | 5 | Similar experience | 4 | 0 | 4 | 5 | 4 | 4
E.2.40 | Capacity (Personal & Resources) | Commissioning manager | 0 | Availability and commitment | 2 | 3 | 4 | 4 | 2 | 2
E.2.41 | Capacity (Personal & Resources) | Commissioning manager | 10 | Total experience | 4 | 4 | 5 | 5 | 5 | 5
E.2.42 | Capacity (Personal & Resources) | Commissioning manager | 5 | Similar experience | 3 | 3 | 5 | 5 | 4 | 5
E.2.43 | Capacity (Personal & Resources) | Procurement manager | 0 | Availability and commitment | 4 | 3 | 4 | 4 | 4 | 4
E.2.44 | Capacity (Personal & Resources) | Procurement manager | 10 | Total experience | 4 | 4 | 3 | 5 | 4 | 5
E.2.45 | Capacity (Personal & Resources) | Procurement manager | 5 | Similar experience | 5 | 2 | 3 | 5 | 5 | 5
E.2.46 | Capacity (Personal & Resources) | Planner/Scheduler | 0 | Availability and commitment | 4 | 3 | 4 | 4 | 4 | 4
E.2.47 | Capacity (Personal & Resources) | Planner/Scheduler | 5 | Total experience | 4 | 3 | 4 | 5 | 3 | 5
E.2.48 | Capacity (Personal & Resources) | Planner/Scheduler | 3 | Similar experience | 4 | 3 | 5 | 5 | 5 | 5
E.3 | Certifications on quality, safety and occupational health program | Certifications on quality, safety and occupational health program | 0 | 0
E.3.1 | Certifications on quality, safety and occupational health program |  | 0 | Certification on quality | 0 | 5 | 1 | 5 | 4 | 5
E.3.2 | Certifications on quality, safety and occupational health program |  | 0 | Certification on safety | 1 | 3 | 1 | 5 | 5 | 5
E.3.3 | Certifications on quality, safety and occupational health program |  | 0 | Certification on OHP | 1 | 0 | 5 | 5 | 5 | 5
E.4 | Training plan | Training plan | 0 | 0
E.4.1 | Training plan |  | 0 | Written eviden | 1 | 5 | 5 | 5 | 3 | 5
E.4.2 | Training plan |  | 0 | Training plan and schedule | 1 | 4 | 5 | 5 | 0 | 3
E.4.3 | Training plan |  | 0 | Knowledge transfer workshop | 0 | 5 | 5 | 5 | 0 | 4
E.5 | Equipment information | Construction Equipment Information | 0 | 0
E.5.1 | Equipment information |  | 0 | Sourcing | 0 | 2 | 5 | 5 | 4 | 2
E.5.2 | Equipment information |  | 0 | Efficiency | 0 | 0 | 5 | 5 | 0 | 5
E.5.3 | Equipment information |  | 0 | Availability | 4 | 5 | 5 | 5 | 2 | 5
E.5.4 | Equipment information |  | 0 | Reliability | 0 | 0 | 5 | 5 | 0 | 5
E.6 | Construction & Installation Manpower | Construction & Installation Manpower | 0 | 0
E.6.1 | Construction & Installation Manpower |  | 0 | Construction manpower | 4 | 5 | 4 | 5 | 4 | 5
E.6.2 | Construction & Installation Manpower |  | 0 | Installation manpower | 4 | 5 | 3 | 5 | 4 | 5

## ABDA
ABDA
ID | Hierachy levels |  |  |  | First Time Assessment |  |  |  | Second Assessment
ID | Level 1 | Level 2 | Level 3 | Level 4 | Score | Score Date | Narrative | Clarification Note | Answer from Bidder | Answered date | Score | Score Date | Final_Score
Total
A | Delivery Plan | 0 | 0 | 0
A.1 | Detailed WBS with schedule and S-curve | 0 | 0 | 0
A.1.1 | Detailed WBS with schedule and S-curve | 0 | 0 | Bidder to follow the WBS defined in ER
A.1.2 | Detailed WBS with schedule and S-curve | 0 | 0 | Sufficiency and completeness of the WBS
A.1.3 | Detailed WBS with schedule and S-curve | 0 | 0 | Schedule is given in required format
A.1.4 | Detailed WBS with schedule and S-curve | 0 | 0 | Interim milestones
A.1.5 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of milestones
A.1.6 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of linkages
A.1.7 | Detailed WBS with schedule and S-curve | 0 | 0 | Consistency with delivery narrative and methodological approach
A.1.8 | Detailed WBS with schedule and S-curve | 0 | 0 | Critical path is highlighted in the schedule program
A.1.9 | Detailed WBS with schedule and S-curve | 0 | 0 | Resources allocation
A.1.10 | Detailed WBS with schedule and S-curve | 0 | 0 | S-curve is probably drawn in the schedule program
A.2 | Delivery Narrative | 0 | 0 | 0
A.2.1 | Delivery Narrative | 0 | 0 | Understanding of the works
A.2.2 | Delivery Narrative | 0 | 0 | Well written and demonstration of approach and delivery of the project
A.2.3 | Delivery Narrative | 0 | 0 | Key activities and deliverables
A.2.4 | Delivery Narrative | 0 | 0 | Feasibility of the approach
A.2.5 | Delivery Narrative | 0 | 0 | Constraints involved with the approach
A.2.6 | Delivery Narrative | 0 | 0 | Resources allocation are persuative and feasible
A.2.7 | Delivery Narrative | 0 | 0 | Advantage of offerred contract strategy
A.2.8 | Delivery Narrative | 0 | 0 | Linkage to deliverable plan (above)
A.2.9 | Delivery Narrative | 0 | 0 | Added value to the Client
A.3 | Safety Plan | 0 | 0 | 0
A.3.1 | Safety Plan | 0 | 0 | Overall Safety Plan
A.3.2 | Safety Plan | 0 | 0 | Safety personnel
A.3.3 | Safety Plan | 0 | 0 | Safety plan for each WP, particularly for critical work items
A.3.4 | Safety Plan | 0 | 0 | Demonstration of historical records, data on safety of previous projects
A.3.5 | Safety Plan | 0 | 0 | Safety compliance to Client's requirement
A.3.6 | Safety Plan | 0 | 0 | Safety compliance to local authority
A.3.7 | Safety Plan | 0 | 0 | Evacuation and immediate actions to follow when safety incident occurs
A.4 | Risk Management Plan (including contingency plan) | 0 | 0 | 0
A.4.1 | Risk Management Plan (including contingency plan) | 0 | 0 | Overall risk management plan
A.4.2 | Risk Management Plan (including contingency plan) | 0 | 0 | Specific risk plan for critical work
A.4.3 | Risk Management Plan (including contingency plan) | 0 | 0 | Understanding risks, particularly during execution on critical items
A.4.4 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk assessment methodology
A.4.5 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk management register and tool
A.4.6 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk removal, reduction, and mitigation plan
A.4.7 | Risk Management Plan (including contingency plan) | 0 | 0 | Feasibility of the overal risk plan
A.5 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | 0
A.5.1 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Completeness of deliverables in tabular format
A.5.2 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Linkage of deliverables to detailed schedule
A.5.3 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Feasibility of the deliverable plan
B | Design | 0 | 0 | 0
B.1 | 0 | M&E | 0 | 0
B.1.1 | Design | M&E | General | QA/QC
B.1.2 | Design | M&E | General | Deliverable Plan
B.1.3 | Design | M&E | General | Value Engineering
B.1.4 | Design | M&E | General | Resource Plan
B.1.5 | Design | M&E | General | Risk and safety in design
B.1.6 | Design | M&E | Intake Chamber | Feasibility
B.1.7 | Design | M&E | Intake Chamber | Constructability
B.1.8 | Design | M&E | Intake Chamber | Correctness
B.1.9 | Design | M&E | Outside Intake Chamber | Feasibility
B.1.10 | Design | M&E | Outside Intake Chamber | Constructability
B.1.11 | Design | M&E | Outside Intake Chamber | Correctness
B.2 | 0 | Automation and Instrumentation (A&I) | 0 | 0
B.2.1 | Design | Automation and Instrumentation (A&I) | General | QA/QC
B.2.2 | Design | Automation and Instrumentation (A&I) | General | Deliverable Plan
B.2.3 | Design | Automation and Instrumentation (A&I) | General | Value Engineering
B.2.4 | Design | Automation and Instrumentation (A&I) | General | Resource Plan
B.2.5 | Design | Automation and Instrumentation (A&I) | General | Risk and safety in design
B.2.6 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Feasibility
B.2.7 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Constructability
B.2.8 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Correctness
B.2.9 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Feasibility
B.2.10 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Constructability
B.2.11 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Correctness
B.3 | 0 | Hydraulics and others | 0 | 0
B.3.1 | Design | Hydraulics and others | General | QA/QC
B.3.2 | Design | Hydraulics and others | General | Deliverable Plan
B.3.3 | Design | Hydraulics and others | General | Value Engineering
B.3.4 | Design | Hydraulics and others | General | Resource Plan
B.3.5 | Design | Hydraulics and others | General | Risk and safety in design
B.3.6 | Design | Hydraulics and others | Intake Chamber | Feasibility
B.3.7 | Design | Hydraulics and others | Intake Chamber | Constructability
B.3.8 | Design | Hydraulics and others | Intake Chamber | Correctness
B.3.9 | Design | Hydraulics and others | Outside Intake Chamber | Feasibility
B.3.10 | Design | Hydraulics and others | Outside Intake Chamber | Constructability
B.3.11 | Design | Hydraulics and others | Outside Intake Chamber | Correctness
B.4 | 0 | Civil/structural design | 0 | 0
B.4.1 | Design | Civil/structural design | General | QA/QC | 4 | 19/12/2022 | - Has clear provisions for QA/QC, Environmental and H&S Requirements (ref. 3.3 and 3.4 page 4-9) | [5 empty] | 4
B.4.2 | Design | 0 | General | Deliverable Plan | 4 | 19/12/2022 | - Has clear understanding of the scope of works - Comprehensive flow of works from preliminary works to move-out (ref. 3.3 and 3.4 page 10-67) - Design Deliverables defined in stages (ref. 2.3 and 2.4 page 16) with review checkpoints | [5 empty] | 4
B.4.3 | Design | 0 | General | Value Engineering
B.4.4 | Design | 0 | General | Resource Plan | 4 | 19/12/2022 | - Sufficient number of key design staff for the entirety of design stages - Efficient allocation with plan provision for possible Stand-by resources (ref. 2.3 and 2.4 page 18) | [5 empty] | 4
B.4.5 | Design | 0 | General | Risk and safety in design | 3 | 19/12/2022 | - Captured only the top 10 significant risks (could be more comprehensive) and has appropriate risk level assessment, mitigation, timetable and monitoring plans (ref 1.4 page 4-14) | [5 empty] | 3
B.4.6 | Design | 0 | Intake Chamber | Feasibility | 4 | 19/12/2022 | - Proposed Methodologies for Civil/Architectural/ Structural disciplines are in-line with known feasible methodologies (ref 3.3 and 3.4 page 10-67) | [5 empty] | 4
B.4.7 | Design | 0 | Intake Chamber | Constructability |  | 19/12/2022
B.4.8 | Design | 0 | Intake Chamber | Correctness | 4 | 19/12/2022 | - Provided calculations incroporating the structural design criteria and design loading considerations from ER | - Mentioned the use of MathCAD R15 and spreadsheet batch calculations, is lead time for wrokshop on these considered in the schedule? |  |  |  |  | 4
B.4.9 | Design | 0 | Outside Intake Chamber | Feasibility | 4 | 19/12/2022 | - Proposed Methodologies for Civil/Architectural/ Structural disciplines are in-line with known feasible methodologies (ref 3.3 and 3.4 page 10-67) | [5 empty] | 4
B.4.10 | Design | 0 | Outside Intake Chamber | Constructability |  | 19/12/2022
B.4.11 | Design | 0 | Outside Intake Chamber | Correctness |  | 19/12/2022
C | Construction/Installation Program and methodology | 0 | 0 | 0
C.1 | 0 | Control System, Automation & Instrumentation | 0 | 0
C.1.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.1.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.1.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.1.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.1.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.2 | 0 | Main Mechanical Works | 0 | 0
C.2.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.2.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.2.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.2.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.2.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.3 | 0 | Main Electrical Works | 0 | 0
C.3.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.3.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.3.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.3.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.3.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.4 | 0 | Piping | 0 | 0
C.4.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.4.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.4.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.4.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.4.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.5 | 0 | Other civil Structure | 0 | 0
C.5.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.5.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.5.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.5.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.5.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
D | Procurement and Installation of long-lead equipment and major process items | Procurement and Installation of long-lead equipment and major process items | 0 | 0
D.1 | 0 | Procurement plan and list of sub-work packages | 0 | 0
D.1.1 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Details of proposed procurement plan
D.1.2 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Supplier detail
D.1.3 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Installation and testing
D.1.4 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Warantty and defect liability
D.1.5 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Feasibility of procurement methodology
D.1.6 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Added value to the Client
D.2 | 0 | Delivery, storage, logistics and materials management plan. | 0 | 0
D.2.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Storage plan on site
D.2.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Losgistic plan
D.3 | 0 | Equipment list | 0 | 0
D.3.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Testing schedule
D.3.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | FAT
D.3.3 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Feasibility of installation method
D.4 | 0 | Service support | 0 | 0
D.4.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Availability of local service support
D.4.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Responsibility of local service support
E | Capacity (Personal & Resources) | Capacity (Personal & Resources) | 0 | 0
E.1 | 0 | Organizational chart | 0 | 0
E.1.1 | Capacity (Personal & Resources) |  | 0 | Overal organization chart | 2 | 2022-12-19 | Some Key Member carries two roles | Why Arsenio Reyes and Mica Ureta has multiple roles? |  |  |  |  | 2
E.1.2 | Capacity (Personal & Resources) |  | 0 | Functional linkage of the chart | 3 | 2022-12-20 | [6 empty] | 3
E.2 | 0 | Key team members | 0 | 0
E.2.1 | Capacity (Personal & Resources) | PM | 0 | Availability and commitment | 3 | 2022-12-19 | Current project 2022, may have conflict with availability | Will sir Abel be able to focus on the project since he is the president of ABDA? |  |  |  |  | 3
E.2.2 | Capacity (Personal & Resources) | PM | 15 | Total Experience (15 years) | 4 | 2022-12-19 | Has 24yrs experience; However, no intake project conducted | [5 empty] | 4
E.2.3 | Capacity (Personal & Resources) | PM | 10 | Similar experience (10 years) | 4 | 2022-12-19 | Experience mostly in conveyance. | [5 empty] | 4
E.2.4 | Capacity (Personal & Resources) | Project Controller | 0 | Availability and commitment | 1 | 2022-12-19 | Has a current multiple project since 2009 (Still in progress) | Will she be able to focus on the project given the 22 projects she has that are still in progress? |  |  |  |  | 1
E.2.5 | Capacity (Personal & Resources) | Project Controller | 10 | Total Experience of the PM (10 years) | 3 | 2022-12-19 | Experiences are still in progress. | [5 empty] | 3
E.2.6 | Capacity (Personal & Resources) | Project Controller | 5 | Similar experience of the PM (5 years) | 4 | 2022-12-19 | Experience mostly in conveyance. | [5 empty] | 4
E.2.7 | Capacity (Personal & Resources) | Safety Manager | 0 | Availability and commitment | 4 | 2022-12-19 | Has 6 On going Projects related to water industry | [5 empty] | 4
E.2.8 | Capacity (Personal & Resources) | Safety Manager | 5 | Total Experience of the PM (10 years) | 4 | 2022-12-19 | 6 years of Experience | [5 empty] | 4
E.2.9 | Capacity (Personal & Resources) | Safety Manager | 3 | Similar experience of the PM (5 years) | 4 | 2022-12-19 | Experience mostly in conveyance. | [5 empty] | 4
E.2.10 | Capacity (Personal & Resources) | Contract Administrator | 0 | Availability and commitment | 1 | 2022-12-19 | Carries two roles for the project. | [5 empty] | 1
E.2.11 | Capacity (Personal & Resources) | Contract Administrator | 10 | Total experience | 3 | 2022-12-19 | 13 years of experience | [5 empty] | 3
E.2.12 | Capacity (Personal & Resources) | Contract Administrator | 5 | Similar experience | 4 | 2022-12-19 | Experience mostly in conveyance. | [5 empty] | 4
E.2.13 | Capacity (Personal & Resources) | Admin assistant Staff | 0 | Availability and commitment | 3 | 2022-12-19 | [6 empty] | 3
E.2.14 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Total experience | 3 | 2022-12-19 | [6 empty] | 3
E.2.15 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Similar experience | 1 | 2022-12-19 | only has 2 years experience in water industry | [5 empty] | 1
E.2.16 | Capacity (Personal & Resources) | Quality manager | 0 | Availability and commitment | 4 | 2022-12-19 | Has accomplished multiple PM, QM AND QS projects | [5 empty] | 4
E.2.17 | Capacity (Personal & Resources) | Quality manager | 10 | Total experience | 4 | 2022-12-19 | 39 years of experience | What are his current roles (2019-2022) in ABDA? |  |  |  |  | 4
E.2.18 | Capacity (Personal & Resources) | Quality manager | 5 | Similar experience | 2 | 2022-12-19 | No experience in QM in WTP projects. Only Distribution | [5 empty] | 2
E.2.19 | Capacity (Personal & Resources) | Design manager | 0 | Availability and commitment | 3 | 2022-12-19 | Has On going Projects as of 2022 | What are his current roles (2019-2022) in ABDA? |  |  |  |  | 3
E.2.20 | Capacity (Personal & Resources) | Design manager | 10 | Total experience | 4 | 2022-12-19 | More than 30 years experience | [5 empty] | 4
E.2.21 | Capacity (Personal & Resources) | Design manager | 5 | Similar experience | 3 | 2022-12-19 | Most Design Projects are related to wastewater, septage, and sewage design. | [5 empty] | 3
E.2.22 | Capacity (Personal & Resources) | Licensed structural engineer | 0 | Availability and commitment | 1 | 2022-12-19 | Cannot Assess Lack of Data | What are his current roles (2019-2022) in ABDA? |  |  |  |  | 1
E.2.23 | Capacity (Personal & Resources) | Licensed structural engineer | 10 | Total experience | 4 | 2022-12-19 | 22 years of Experience | [5 empty] | 4
E.2.24 | Capacity (Personal & Resources) | Licensed structural engineer | 5 | Similar experience | 4 | 2022-12-19 | Has 9 years experience varying from Plant expansion, 88 MLD Water Recycling Facility, 50 MLD Water Treatment Facility and STP projects | [5 empty] | 4
E.2.25 | Capacity (Personal & Resources) | Hydraulic engineer | 0 | Availability and commitment | 4 | 2022-12-19 | Major Projects are mostly Accomplished | [5 empty] | 4
E.2.26 | Capacity (Personal & Resources) | Hydraulic engineer | 10 | Total experience | 4 | 2022-12-19 | Has 15 Years of Experience mostly related to water | [5 empty] | 4
E.2.27 | Capacity (Personal & Resources) | Hydraulic engineer | 5 | Similar experience | 4 | 2022-12-19 | Major Project: 600 MLD Kaliwa WATER Conveyance System. Most of its experience are in Conveyance and STP. | [5 empty] | 4
E.2.28 | Capacity (Personal & Resources) | Licensed mech engineer | 0 | Availability and commitment | 2 | 2022-12-19 | Currently has multiple Projects ongoing from year 2015 - Present | [5 empty] | 2
E.2.29 | Capacity (Personal & Resources) | Licensed mech engineer | 10 | Total experience | 4 | 2022-12-19 | Has 21 Years experience in Power Plant, Water Industry Projects, MEPF Design | [5 empty] | 4
E.2.30 | Capacity (Personal & Resources) | Licensed mech engineer | 5 | Similar experience | 4 | 2022-12-19 | Has Multiple Ongoing Projects from pumping stations, WTP, STP, and Lift Stations | [5 empty] | 4
E.2.31 | Capacity (Personal & Resources) | Licensed elec engineer | 0 | Availability and commitment | 2 | 2022-12-19 | Has On going Projects as of 2022 | What are his current roles as of 2019 -Present? |  |  |  |  | 2
E.2.32 | Capacity (Personal & Resources) | Licensed elec engineer | 10 | Total experience | 4 | 2022-12-19 | More that 40 years of Experience varying from Power to Water industry | [5 empty] | 4
E.2.33 | Capacity (Personal & Resources) | Licensed elec engineer | 5 | Similar experience | 3 | 2022-12-19 | Relevant Experience are Deepwell, WTP, and Pumping stations | Details on the Project experience ( How big in terms of MLD?) State atleast 1 Major Project |  |  |  |  | 3
E.2.34 | Capacity (Personal & Resources) | A&I engineer | 0 | Availability and commitment | 2 | 2022-12-19 | Has an Ongoing Project since 2007, and does not have any data regarding its current role | What are his current roles as of 2019 -Present? |  |  |  |  | 2
E.2.35 | Capacity (Personal & Resources) | A&I engineer | 10 | Total experience | 3 | 2022-12-19 | Has 15 years of Experience | [5 empty] | 3
E.2.36 | Capacity (Personal & Resources) | A&I engineer | 5 | Similar experience | 1 | 2022-12-19 | Does not have any experience in any water projects | What are his current projects in Water Industry? There are no indicated Projects. |  |  |  |  | 1
E.2.37 | Capacity (Personal & Resources) | Construction Manager | 0 | Availability and commitment | 1 | 2022-12-19 | Incomplete data about current projects. Cannot assess commitment and availability | What are his roles and current projects in year 2019-2022? |  |  |  |  | 1
E.2.38 | Capacity (Personal & Resources) | Construction Manager | 10 | Total experience | 4 | 2022-12-19 | Has 22 Years of relevant experience in Construction Management | [5 empty] | 4
E.2.39 | Capacity (Personal & Resources) | Construction Manager | 5 | Similar experience | 4 | 2022-12-19 | Able to get experience in 1.2M Transmission in Qatar, and 50 MLD pump station project | [5 empty] | 4
E.2.40 | Capacity (Personal & Resources) | Commissioning manager | 0 | Availability and commitment | 2 | 2022-12-19 | Has On going Projects as of 2022 | What are his current roles as of 2019 -Present? |  |  |  |  | 2
E.2.41 | Capacity (Personal & Resources) | Commissioning manager | 10 | Total experience | 4 | 2022-12-19 | More that 40 years of Experience varying from Power to Water industry | [5 empty] | 4
E.2.42 | Capacity (Personal & Resources) | Commissioning manager | 5 | Similar experience | 3 | 2022-12-19 | Relevant Experience are Deepwell, WTP, and Pumping stations | Details on the Project experience ( How big in terms of MLD?) State atleast 1 Major Project |  |  |  |  | 3
E.2.43 | Capacity (Personal & Resources) | Procurement manager | 0 | Availability and commitment | 4 | 2022-12-19 | Has ongoing Projects related to water industry | [5 empty] | 4
E.2.44 | Capacity (Personal & Resources) | Procurement manager | 10 | Total experience | 4 | 2022-12-19 | 14 Years experience related to water network projects | [5 empty] | 4
E.2.45 | Capacity (Personal & Resources) | Procurement manager | 5 | Similar experience | 5 | 2022-12-19 | Most experience are related to Water network projects | [5 empty] | 5
E.2.46 | Capacity (Personal & Resources) | Planner/Scheduler | 0 | Availability and commitment | 4 | 2022-12-19 | Has Ongoing Pipelaying Project | [5 empty] | 4
E.2.47 | Capacity (Personal & Resources) | Planner/Scheduler | 5 | Total experience | 4 | 2022-12-19 | 18 Years in Construction industry | [5 empty] | 4
E.2.48 | Capacity (Personal & Resources) | Planner/Scheduler | 3 | Similar experience | 4 | 2022-12-19 | Highest Project is a 150MLD WTP Facility and managed a 500 Million Value Contract | [5 empty] | 4
E.3 | Certifications on quality, safety and occupational health program | Certifications on quality, safety and occupational health program | 0 | 0
E.3.1 | Certifications on quality, safety and occupational health program |  | 0 | Certification on quality | 0 | 2022-12-19 | No Shown Quality Certification programs | Does any body have Quality Program Training? |  |  |  |  | 0
E.3.2 | Certifications on quality, safety and occupational health program |  | 0 | Certification on safety | 1 | 2022-12-19 | Only 2 Key Member were only to obtain COSH | Does other Key members have COSH Trainings? |  |  |  |  | 1
E.3.3 | Certifications on quality, safety and occupational health program |  | 0 | Certification on OHP | 1 | 2022-12-19 | Only 1 has OHP Training | Does other Key members have OHP Trainings? |  |  |  |  | 1
E.4 | Training plan | Training plan | 0 | 0
E.4.1 | Training plan |  | 0 | Written eviden | 1 | 2022-12-19 | Only H&S Training are Provided | [5 empty] | 1
E.4.2 | Training plan |  | 0 | Training plan and schedule | 1 | 2022-12-19 | Does not provide provide any syllabus/ schema of the training plan | [5 empty] | 1
E.4.3 | Training plan |  | 0 | Knowledge transfer workshop | 0 | 2022-12-19 | No Provided Knowledge Transfer Workshop | [5 empty] | 0
E.5 | Equipment information | Construction Equipment Information | 0 | 0
E.5.1 | Equipment information |  | 0 | Sourcing | 0 | 2022-12-19 | No Provided contractor for sourcing of Equipment | [5 empty] | 0
E.5.2 | Equipment information |  | 0 | Efficiency | 0 | 2022-12-19 | No Provided Certificate of Operation and Maintenance of Equipment | [5 empty] | 0
E.5.3 | Equipment information |  | 0 | Availability | 4 | 2022-12-19 | All needed equipment are stated and available | [5 empty] | 4
E.5.4 | Equipment information |  | 0 | Reliability | 0 | 2022-12-19 | No Provided Certificate of Operation and Maintenance of Equipment | [5 empty] | 0
E.6 | Construction & Installation Manpower | Construction & Installation Manpower | 0 | 0
E.6.1 | Construction & Installation Manpower |  | 0 | Construction manpower | 4 | 2022-12-19 | Adequate Manpower | [5 empty] | 4
E.6.2 | Construction & Installation Manpower |  | 0 | Installation manpower | 4 | 2022-12-19 | Adequate Manpower | [5 empty] | 4

## DATEM
DATEM
ID | Hierachy levels |  |  |  | First Time Assessment |  |  |  | Second Assessment
ID | Level 1 | Level 2 | Level 3 | Level 4 | Score | Score Date | Narrative | Clarification Note | Answer from Bidder | Answered date | Score | Score Date | Final_Score
Total
A | Delivery Plan | 0 | 0 | 0
A.1 | Detailed WBS with schedule and S-curve | 0 | 0 | 0
A.1.1 | Detailed WBS with schedule and S-curve | 0 | 0 | Bidder to follow the WBS defined in ER
A.1.2 | Detailed WBS with schedule and S-curve | 0 | 0 | Sufficiency and completeness of the WBS
A.1.3 | Detailed WBS with schedule and S-curve | 0 | 0 | Schedule is given in required format
A.1.4 | Detailed WBS with schedule and S-curve | 0 | 0 | Interim milestones
A.1.5 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of milestones
A.1.6 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of linkages
A.1.7 | Detailed WBS with schedule and S-curve | 0 | 0 | Consistency with delivery narrative and methodological approach
A.1.8 | Detailed WBS with schedule and S-curve | 0 | 0 | Critical path is highlighted in the schedule program
A.1.9 | Detailed WBS with schedule and S-curve | 0 | 0 | Resources allocation
A.1.10 | Detailed WBS with schedule and S-curve | 0 | 0 | S-curve is probably drawn in the schedule program
A.2 | Delivery Narrative | 0 | 0 | 0
A.2.1 | Delivery Narrative | 0 | 0 | Understanding of the works
A.2.2 | Delivery Narrative | 0 | 0 | Well written and demonstration of approach and delivery of the project
A.2.3 | Delivery Narrative | 0 | 0 | Key activities and deliverables
A.2.4 | Delivery Narrative | 0 | 0 | Feasibility of the approach
A.2.5 | Delivery Narrative | 0 | 0 | Constraints involved with the approach
A.2.6 | Delivery Narrative | 0 | 0 | Resources allocation are persuative and feasible
A.2.7 | Delivery Narrative | 0 | 0 | Advantage of offerred contract strategy
A.2.8 | Delivery Narrative | 0 | 0 | Linkage to deliverable plan (above)
A.2.9 | Delivery Narrative | 0 | 0 | Added value to the Client
A.3 | Safety Plan | 0 | 0 | 0
A.3.1 | Safety Plan | 0 | 0 | Overall Safety Plan
A.3.2 | Safety Plan | 0 | 0 | Safety personnel
A.3.3 | Safety Plan | 0 | 0 | Safety plan for each WP, particularly for critical work items
A.3.4 | Safety Plan | 0 | 0 | Demonstration of historical records, data on safety of previous projects
A.3.5 | Safety Plan | 0 | 0 | Safety compliance to Client's requirement
A.3.6 | Safety Plan | 0 | 0 | Safety compliance to local authority
A.3.7 | Safety Plan | 0 | 0 | Evacuation and immediate actions to follow when safety incident occurs
A.4 | Risk Management Plan (including contingency plan) | 0 | 0 | 0
A.4.1 | Risk Management Plan (including contingency plan) | 0 | 0 | Overall risk management plan
A.4.2 | Risk Management Plan (including contingency plan) | 0 | 0 | Specific risk plan for critical work
A.4.3 | Risk Management Plan (including contingency plan) | 0 | 0 | Understanding risks, particularly during execution on critical items
A.4.4 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk assessment methodology
A.4.5 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk management register and tool
A.4.6 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk removal, reduction, and mitigation plan
A.4.7 | Risk Management Plan (including contingency plan) | 0 | 0 | Feasibility of the overal risk plan
A.5 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | 0
A.5.1 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Completeness of deliverables in tabular format
A.5.2 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Linkage of deliverables to detailed schedule
A.5.3 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Feasibility of the deliverable plan
B | Design | 0 | 0 | 0
B.1 | 0 | M&E | 0 | 0
B.1.1 | Design | M&E | General | QA/QC
B.1.2 | Design | M&E | General | Deliverable Plan
B.1.3 | Design | M&E | General | Value Engineering
B.1.4 | Design | M&E | General | Resource Plan
B.1.5 | Design | M&E | General | Risk and safety in design
B.1.6 | Design | M&E | Intake Chamber | Feasibility
B.1.7 | Design | M&E | Intake Chamber | Constructability
B.1.8 | Design | M&E | Intake Chamber | Correctness
B.1.9 | Design | M&E | Outside Intake Chamber | Feasibility
B.1.10 | Design | M&E | Outside Intake Chamber | Constructability
B.1.11 | Design | M&E | Outside Intake Chamber | Correctness
B.2 | 0 | Automation and Instrumentation (A&I) | 0 | 0
B.2.1 | Design | Automation and Instrumentation (A&I) | General | QA/QC
B.2.2 | Design | Automation and Instrumentation (A&I) | General | Deliverable Plan
B.2.3 | Design | Automation and Instrumentation (A&I) | General | Value Engineering
B.2.4 | Design | Automation and Instrumentation (A&I) | General | Resource Plan
B.2.5 | Design | Automation and Instrumentation (A&I) | General | Risk and safety in design
B.2.6 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Feasibility
B.2.7 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Constructability
B.2.8 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Correctness
B.2.9 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Feasibility
B.2.10 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Constructability
B.2.11 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Correctness
B.3 | 0 | Hydraulics and others | 0 | 0
B.3.1 | Design | Hydraulics and others | General | QA/QC
B.3.2 | Design | Hydraulics and others | General | Deliverable Plan
B.3.3 | Design | Hydraulics and others | General | Value Engineering
B.3.4 | Design | Hydraulics and others | General | Resource Plan
B.3.5 | Design | Hydraulics and others | General | Risk and safety in design
B.3.6 | Design | Hydraulics and others | Intake Chamber | Feasibility
B.3.7 | Design | Hydraulics and others | Intake Chamber | Constructability
B.3.8 | Design | Hydraulics and others | Intake Chamber | Correctness
B.3.9 | Design | Hydraulics and others | Outside Intake Chamber | Feasibility
B.3.10 | Design | Hydraulics and others | Outside Intake Chamber | Constructability
B.3.11 | Design | Hydraulics and others | Outside Intake Chamber | Correctness
B.4 | 0 | Civil/structural design | 0 | 0
B.4.1 | Design | Civil/structural design | General | QA/QC | 2 | 19/12/2022 | - QA/QC | [5 empty] | 2
B.4.2 | Design | 0 | General | Deliverable Plan
B.4.3 | Design | 0 | General | Value Engineering
B.4.4 | Design | 0 | General | Resource Plan
B.4.5 | Design | 0 | General | Risk and safety in design | 4 | 19/12/2022 | - Comprehensive identification of significant risks, proper management/mitigation (ref hazards mitigation, hirac, risk contingency plan) | [5 empty] | 4
B.4.6 | Design | 0 | Intake Chamber | Feasibility
B.4.7 | Design | 0 | Intake Chamber | Constructability
B.4.8 | Design | 0 | Intake Chamber | Correctness | 2 | 19/12/2022 | - Partially complete as only plan and section drawings are submitted (ref 2.iv structural design pdf) | - Where is the calculation? ' - No visibility on used software for calculation, design criteria, and loading considerations. |  |  |  |  | 2
B.4.9 | Design | 0 | Outside Intake Chamber | Feasibility | 0 | 19/12/2022 | - No installation methodology were provided for intake pipe | [5 empty] | 0
B.4.10 | Design | 0 | Outside Intake Chamber | Constructability | 0 | 19/12/2022 | - No installation methodology were provided for intake pipe | [5 empty] | 0
B.4.11 | Design | 0 | Outside Intake Chamber | Correctness | 0 | 19/12/2022 | - No calculations/specifications/drawings were provided for intake pipe | [5 empty] | 0
C | Construction/Installation Program and methodology | 0 | 0 | 0
C.1 | 0 | Control System, Automation & Instrumentation | 0 | 0
C.1.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.1.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.1.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.1.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.1.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.2 | 0 | Main Mechanical Works | 0 | 0
C.2.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.2.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.2.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.2.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.2.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.3 | 0 | Main Electrical Works | 0 | 0
C.3.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.3.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.3.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.3.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.3.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.4 | 0 | Piping | 0 | 0
C.4.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.4.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.4.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.4.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.4.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.5 | 0 | Other civil Structure | 0 | 0
C.5.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.5.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.5.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.5.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.5.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
D | Procurement and Installation of long-lead equipment and major process items | Procurement and Installation of long-lead equipment and major process items | 0 | 0
D.1 | 0 | Procurement plan and list of sub-work packages | 0 | 0
D.1.1 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Details of proposed procurement plan
D.1.2 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Supplier detail
D.1.3 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Installation and testing
D.1.4 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Warantty and defect liability
D.1.5 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Feasibility of procurement methodology
D.1.6 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Added value to the Client
D.2 | 0 | Delivery, storage, logistics and materials management plan. | 0 | 0
D.2.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Storage plan on site
D.2.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Losgistic plan
D.3 | 0 | Equipment list | 0 | 0
D.3.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Testing schedule
D.3.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | FAT
D.3.3 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Feasibility of installation method
D.4 | 0 | Service support | 0 | 0
D.4.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Availability of local service support
D.4.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Responsibility of local service support
E | Capacity (Personal & Resources) | Capacity (Personal & Resources) | 0 | 0
E.1 | 0 | Organizational chart | 0 | 0
E.1.1 | Capacity (Personal & Resources) |  | 0 | Overal organization chart | 4 | 12/20/2022 | Complete with all of the employee requirements | [5 empty] | 4
E.1.2 | Capacity (Personal & Resources) |  | 0 | Functional linkage of the chart | 5 | 12/20/2022 | Coordination and structure is good | [5 empty] | 5
E.2 | 0 | Key team members | 0 | 0
E.2.1 | Capacity (Personal & Resources) | PM | 0 | Availability and commitment | 4 | 12/20/2022 | Acting as Division Head | [5 empty] | 4
E.2.2 | Capacity (Personal & Resources) | PM | 15 | Total Experience (15 years) | 4 | 12/20/2022 | 27 Years of Experience on different construction projects | [5 empty] | 4
E.2.3 | Capacity (Personal & Resources) | PM | 10 | Similar experience (10 years) | 2 | 12/20/2022 | Lacking of Experience in Water Industry. Closest Project is a 75 MLD STP Facility | [5 empty] | 2
E.2.4 | Capacity (Personal & Resources) | Project Controller | 0 | Availability and commitment | 3 | 12/20/2022 | Does not have any data on its current projects | What are his ongoing projects? |  |  |  |  | 3
E.2.5 | Capacity (Personal & Resources) | Project Controller | 10 | Total Experience of the PM (10 years) | 3 | 12/20/2022 | Met ten years of experience with major projects at hand | [5 empty] | 3
E.2.6 | Capacity (Personal & Resources) | Project Controller | 5 | Similar experience of the PM (5 years) | 2 | 12/20/2022 | Only 1 relative experience on water industry (Retrofit of 1250 MLD) | [5 empty] | 2
E.2.7 | Capacity (Personal & Resources) | Safety Manager | 0 | Availability and commitment | 3 | 12/20/2022 | Currently managing all projects of DATEM | [5 empty] | 3
E.2.8 | Capacity (Personal & Resources) | Safety Manager | 5 | Total Experience of the PM (10 years) | 4 | 12/20/2022 | Have adequate experience in H&S on PM | [5 empty] | 4
E.2.9 | Capacity (Personal & Resources) | Safety Manager | 3 | Similar experience of the PM (5 years) | 2 | 12/20/2022 | Has Multiple projects handled but not related to Water Industry | [5 empty] | 2
E.2.10 | Capacity (Personal & Resources) | Contract Administrator | 0 | Availability and commitment | 4 | 12/20/2022 | [6 empty] | 4
E.2.11 | Capacity (Personal & Resources) | Contract Administrator | 10 | Total experience | 2 | 12/20/2022 | Has 10 years experience in construction | [5 empty] | 2
E.2.12 | Capacity (Personal & Resources) | Contract Administrator | 5 | Similar experience | 0 | 12/20/2022 | No data | What are the projects handled? |  |  |  |  | 0
E.2.13 | Capacity (Personal & Resources) | Admin assistant Staff | 0 | Availability and commitment | 4 | 12/20/2022 | [6 empty] | 4
E.2.14 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Total experience | 4 | 12/20/2022 | [6 empty] | 4
E.2.15 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Similar experience | 0 | 12/20/2022 | No Water Industry Projects Handled | [5 empty] | 0
E.2.16 | Capacity (Personal & Resources) | Quality manager | 0 | Availability and commitment | 3 | 12/20/2022 | Has an on going Major Project which could conflict availability | [5 empty] | 3
E.2.17 | Capacity (Personal & Resources) | Quality manager | 10 | Total experience | 4 | 12/20/2022 | Has more than 20 years of experience involving on big projects | [5 empty] | 4
E.2.18 | Capacity (Personal & Resources) | Quality manager | 5 | Similar experience | 0 | 12/20/2022 | No Project related to water industry (STP, WTP, PUMP FACILITY. ETC. ) | How will the proposed staff be able to qualify quality in water projects if he has no background on major water projects? |  |  |  |  | 0
E.2.19 | Capacity (Personal & Resources) | Design manager | 0 | Availability and commitment | 0 | 12/20/2022 | No Data of the nominees current project | Why he is also the structural engineer? This could lead to conflict of interest |  |  |  |  | 0
E.2.20 | Capacity (Personal & Resources) | Design manager | 10 | Total experience | 3 | 12/20/2022 | Has more than 10 years experience in design engineering analysis | [5 empty] | 3
E.2.21 | Capacity (Personal & Resources) | Design manager | 5 | Similar experience | 4 | 12/20/2022 | His experience in water industry are mainly in STP facilities | [5 empty] | 4
E.2.22 | Capacity (Personal & Resources) | Licensed structural engineer | 0 | Availability and commitment | 0 | 12/20/2022 | No Data of the nominees current project | Why is he also the design manager? This could lead to conflict of interest |  |  |  |  | 0
E.2.23 | Capacity (Personal & Resources) | Licensed structural engineer | 10 | Total experience | 3 | 12/20/2022 | Has more than 10 years experience in design engineering analysis | [5 empty] | 3
E.2.24 | Capacity (Personal & Resources) | Licensed structural engineer | 5 | Similar experience | 4 | 12/20/2022 | His experience in water industry are mainly in STP facilities | [5 empty] | 4
E.2.25 | Capacity (Personal & Resources) | Hydraulic engineer | 0 | Availability and commitment | 4 | 12/20/2022 | Based on his CV, no major projects that could conflict with his availability in the project | [5 empty] | 4
E.2.26 | Capacity (Personal & Resources) | Hydraulic engineer | 10 | Total experience | 4 | 12/20/2022 | Has 14 years of experience | [5 empty] | 4
E.2.27 | Capacity (Personal & Resources) | Hydraulic engineer | 5 | Similar experience | 4 | 12/20/2022 | His past experience are mostly involved in Water industry Projects. (1500 MLD- La Mesa Dam WTP 1) | [5 empty] | 4
E.2.28 | Capacity (Personal & Resources) | Licensed mech engineer | 0 | Availability and commitment | 3 | 12/20/2022 | Currently Handling a small Water Industry Project | [5 empty] | 3
E.2.29 | Capacity (Personal & Resources) | Licensed mech engineer | 10 | Total experience | 4 | 12/20/2022 | At least 20 years of experience in the industry | [5 empty] | 4
E.2.30 | Capacity (Personal & Resources) | Licensed mech engineer | 5 | Similar experience | 3 | 12/20/2022 | Projects related to water are too small and does not meet general requirements for Mechanical Engineer set by Manila Water | [5 empty] | 3
E.2.31 | Capacity (Personal & Resources) | Licensed elec engineer | 0 | Availability and commitment | 2 | 12/20/2022 | Has Current Projects related to water indsutry | [5 empty] | 2
E.2.32 | Capacity (Personal & Resources) | Licensed elec engineer | 10 | Total experience | 4 | 12/20/2022 | More than 25 years of experience mainly on water industry | [5 empty] | 4
E.2.33 | Capacity (Personal & Resources) | Licensed elec engineer | 5 | Similar experience | 4 | 12/20/2022 | Most of his experience are relate to water industry projects. (Biggest: 30MLD Bulk Water Treatment plant - Butuan) | [5 empty] | 4
E.2.34 | Capacity (Personal & Resources) | A&I engineer | 0 | Availability and commitment | 4 | 12/20/2022 | [6 empty] | 4
E.2.35 | Capacity (Personal & Resources) | A&I engineer | 10 | Total experience | 4 | 12/20/2022 | 15 years of experience varying on water industry petroleum, and building construction in A&I Design and Build | [5 empty] | 4
E.2.36 | Capacity (Personal & Resources) | A&I engineer | 5 | Similar experience | 4 | 12/20/2022 | Has experience involving in design of 150 and 200 MLD Projects. | [5 empty] | 4
E.2.37 | Capacity (Personal & Resources) | Construction Manager | 0 | Availability and commitment | 2 | 12/20/2022 | Commitment is key issue since the proposed staff is involved in a major project | [5 empty] | 2
E.2.38 | Capacity (Personal & Resources) | Construction Manager | 10 | Total experience | 3 | 12/20/2022 | Has 11 years of Experience | [5 empty] | 3
E.2.39 | Capacity (Personal & Resources) | Construction Manager | 5 | Similar experience | 0 | 12/20/2022 | No Experience related to any water industry projects | [5 empty] | 0
E.2.40 | Capacity (Personal & Resources) | Commissioning manager | 0 | Availability and commitment | 3 | 12/20/2022 | Availability of the Proposed staff can be an issue since she is involved in multiple large scale projects | [5 empty] | 3
E.2.41 | Capacity (Personal & Resources) | Commissioning manager | 10 | Total experience | 4 | 12/20/2022 | More than 20 years of experience from water industry to high rise construction | [5 empty] | 4
E.2.42 | Capacity (Personal & Resources) | Commissioning manager | 5 | Similar experience | 3 | 12/20/2022 | Relevant experience are on par and has involvement on water projects (Biggest: 30 MLD) | [5 empty] | 3
E.2.43 | Capacity (Personal & Resources) | Procurement manager | 0 | Availability and commitment | 3 | 12/20/2022 | Availability of the Proposed staff can be an issue since she is involved in multiple large scale projects | [5 empty] | 3
E.2.44 | Capacity (Personal & Resources) | Procurement manager | 10 | Total experience | 4 | 12/20/2022 | Has more than 20 years experience in procurement | [5 empty] | 4
E.2.45 | Capacity (Personal & Resources) | Procurement manager | 5 | Similar experience | 2 | 12/20/2022 | No experience in any water industry related projects | [5 empty] | 2
E.2.46 | Capacity (Personal & Resources) | Planner/Scheduler | 0 | Availability and commitment | 3 | 12/20/2022 | Availability of the Proposed staff can be an issue since she is involved in multiple large scale projects | [5 empty] | 3
E.2.47 | Capacity (Personal & Resources) | Planner/Scheduler | 5 | Total experience | 3 | 12/20/2022 | Has 15 years experience in multiple construction projects | [5 empty] | 3
E.2.48 | Capacity (Personal & Resources) | Planner/Scheduler | 3 | Similar experience | 3 | 12/20/2022 | No experiencei n any water industry related projects | [5 empty] | 3
E.3 | Certifications on quality, safety and occupational health program | Certifications on quality, safety and occupational health program | 0 | 0
E.3.1 | Certifications on quality, safety and occupational health program |  | 0 | Certification on quality | 5 | 12/20/2022 | Provided ISO certificate for Quality Management | [5 empty] | 5
E.3.2 | Certifications on quality, safety and occupational health program |  | 0 | Certification on safety | 3 | 12/20/2022 | Did not provide certificate for Safety but most keymembers have COSH Training and practitioners | [5 empty] | 3
E.3.3 | Certifications on quality, safety and occupational health program |  | 0 | Certification on OHP | 0 | 12/20/2022 | Did not provide certificate for OHP | [5 empty] | 0
E.4 | Training plan | Training plan | 0 | 0
E.4.1 | Training plan |  | 0 | Written eviden | 5 | 12/20/2022 | Provided documents showing evidence of conduction of training | [5 empty] | 5
E.4.2 | Training plan |  | 0 | Training plan and schedule | 4 | 12/20/2022 | Provided schema for training plan but in general only | [5 empty] | 4
E.4.3 | Training plan |  | 0 | Knowledge transfer workshop | 5 | 12/20/2022 | Provided multiple leadership workshop trainings | [5 empty] | 5
E.5 | Equipment information | Construction Equipment Information | 0 | 0
E.5.1 | Equipment information |  | 0 | Sourcing | 2 |  | Did not provide provider of heavy equipment | [5 empty] | 2
E.5.2 | Equipment information |  | 0 | Efficiency | 0 |  | Did not provide certificates and proof of documents of quality | [5 empty] | 0
E.5.3 | Equipment information |  | 0 | Availability | 5 |  | Provided Acquisition date, equipment schedule and availability | [5 empty] | 5
E.5.4 | Equipment information |  | 0 | Reliability | 0 |  | failure to provide certificate to operate | [5 empty] | 0
E.6 | Construction & Installation Manpower | Construction & Installation Manpower | 0 | 0
E.6.1 | Construction & Installation Manpower |  | 0 | Construction manpower | 5 |  | Manpower is adequate and comparable to other biddrs | [5 empty] | 5
E.6.2 | Construction & Installation Manpower |  | 0 | Installation manpower | 5 |  | Manpower is adequate and comparable to other biddrs | [5 empty] | 5

## DMCI
DMCI
ID | Hierachy levels |  |  |  | First Time Assessment |  |  |  | Second Assessment
ID | Level 1 | Level 2 | Level 3 | Level 4 | Score | Score Date | Narrative | Clarification Note | Answer from Bidder | Answered date | Score | Score Date | Final_Score
Total
A | Delivery Plan | 0 | 0 | 0
A.1 | Detailed WBS with schedule and S-curve | 0 | 0 | 0
A.1.1 | Detailed WBS with schedule and S-curve | 0 | 0 | Bidder to follow the WBS defined in ER
A.1.2 | Detailed WBS with schedule and S-curve | 0 | 0 | Sufficiency and completeness of the WBS
A.1.3 | Detailed WBS with schedule and S-curve | 0 | 0 | Schedule is given in required format
A.1.4 | Detailed WBS with schedule and S-curve | 0 | 0 | Interim milestones
A.1.5 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of milestones
A.1.6 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of linkages
A.1.7 | Detailed WBS with schedule and S-curve | 0 | 0 | Consistency with delivery narrative and methodological approach
A.1.8 | Detailed WBS with schedule and S-curve | 0 | 0 | Critical path is highlighted in the schedule program
A.1.9 | Detailed WBS with schedule and S-curve | 0 | 0 | Resources allocation
A.1.10 | Detailed WBS with schedule and S-curve | 0 | 0 | S-curve is probably drawn in the schedule program
A.2 | Delivery Narrative | 0 | 0 | 0
A.2.1 | Delivery Narrative | 0 | 0 | Understanding of the works
A.2.2 | Delivery Narrative | 0 | 0 | Well written and demonstration of approach and delivery of the project
A.2.3 | Delivery Narrative | 0 | 0 | Key activities and deliverables
A.2.4 | Delivery Narrative | 0 | 0 | Feasibility of the approach
A.2.5 | Delivery Narrative | 0 | 0 | Constraints involved with the approach
A.2.6 | Delivery Narrative | 0 | 0 | Resources allocation are persuative and feasible
A.2.7 | Delivery Narrative | 0 | 0 | Advantage of offerred contract strategy
A.2.8 | Delivery Narrative | 0 | 0 | Linkage to deliverable plan (above)
A.2.9 | Delivery Narrative | 0 | 0 | Added value to the Client
A.3 | Safety Plan | 0 | 0 | 0
A.3.1 | Safety Plan | 0 | 0 | Overall Safety Plan
A.3.2 | Safety Plan | 0 | 0 | Safety personnel
A.3.3 | Safety Plan | 0 | 0 | Safety plan for each WP, particularly for critical work items
A.3.4 | Safety Plan | 0 | 0 | Demonstration of historical records, data on safety of previous projects
A.3.5 | Safety Plan | 0 | 0 | Safety compliance to Client's requirement
A.3.6 | Safety Plan | 0 | 0 | Safety compliance to local authority
A.3.7 | Safety Plan | 0 | 0 | Evacuation and immediate actions to follow when safety incident occurs
A.4 | Risk Management Plan (including contingency plan) | 0 | 0 | 0
A.4.1 | Risk Management Plan (including contingency plan) | 0 | 0 | Overall risk management plan
A.4.2 | Risk Management Plan (including contingency plan) | 0 | 0 | Specific risk plan for critical work
A.4.3 | Risk Management Plan (including contingency plan) | 0 | 0 | Understanding risks, particularly during execution on critical items
A.4.4 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk assessment methodology
A.4.5 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk management register and tool
A.4.6 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk removal, reduction, and mitigation plan
A.4.7 | Risk Management Plan (including contingency plan) | 0 | 0 | Feasibility of the overal risk plan
A.5 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | 0
A.5.1 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Completeness of deliverables in tabular format
A.5.2 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Linkage of deliverables to detailed schedule
A.5.3 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Feasibility of the deliverable plan
B | Design | 0 | 0 | 0
B.1 | 0 | M&E | 0 | 0
B.1.1 | Design | M&E | General | QA/QC
B.1.2 | Design | M&E | General | Deliverable Plan
B.1.3 | Design | M&E | General | Value Engineering
B.1.4 | Design | M&E | General | Resource Plan
B.1.5 | Design | M&E | General | Risk and safety in design
B.1.6 | Design | M&E | Intake Chamber | Feasibility
B.1.7 | Design | M&E | Intake Chamber | Constructability
B.1.8 | Design | M&E | Intake Chamber | Correctness
B.1.9 | Design | M&E | Outside Intake Chamber | Feasibility
B.1.10 | Design | M&E | Outside Intake Chamber | Constructability
B.1.11 | Design | M&E | Outside Intake Chamber | Correctness
B.2 | 0 | Automation and Instrumentation (A&I) | 0 | 0
B.2.1 | Design | Automation and Instrumentation (A&I) | General | QA/QC
B.2.2 | Design | Automation and Instrumentation (A&I) | General | Deliverable Plan
B.2.3 | Design | Automation and Instrumentation (A&I) | General | Value Engineering
B.2.4 | Design | Automation and Instrumentation (A&I) | General | Resource Plan
B.2.5 | Design | Automation and Instrumentation (A&I) | General | Risk and safety in design
B.2.6 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Feasibility
B.2.7 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Constructability
B.2.8 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Correctness
B.2.9 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Feasibility
B.2.10 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Constructability
B.2.11 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Correctness
B.3 | 0 | Hydraulics and others | 0 | 0
B.3.1 | Design | Hydraulics and others | General | QA/QC
B.3.2 | Design | Hydraulics and others | General | Deliverable Plan
B.3.3 | Design | Hydraulics and others | General | Value Engineering
B.3.4 | Design | Hydraulics and others | General | Resource Plan
B.3.5 | Design | Hydraulics and others | General | Risk and safety in design
B.3.6 | Design | Hydraulics and others | Intake Chamber | Feasibility
B.3.7 | Design | Hydraulics and others | Intake Chamber | Constructability
B.3.8 | Design | Hydraulics and others | Intake Chamber | Correctness
B.3.9 | Design | Hydraulics and others | Outside Intake Chamber | Feasibility
B.3.10 | Design | Hydraulics and others | Outside Intake Chamber | Constructability
B.3.11 | Design | Hydraulics and others | Outside Intake Chamber | Correctness
B.4 | 0 | Civil/structural design | 0 | 0
B.4.1 | Design | Civil/structural design | General | QA/QC
B.4.2 | Design | 0 | General | Deliverable Plan
B.4.3 | Design | 0 | General | Value Engineering
B.4.4 | Design | 0 | General | Resource Plan
B.4.5 | Design | 0 | General | Risk and safety in design
B.4.6 | Design | 0 | Intake Chamber | Feasibility
B.4.7 | Design | 0 | Intake Chamber | Constructability
B.4.8 | Design | 0 | Intake Chamber | Correctness
B.4.9 | Design | 0 | Outside Intake Chamber | Feasibility
B.4.10 | Design | 0 | Outside Intake Chamber | Constructability
B.4.11 | Design | 0 | Outside Intake Chamber | Correctness
C | Construction/Installation Program and methodology | 0 | 0 | 0
C.1 | 0 | Control System, Automation & Instrumentation | 0 | 0
C.1.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.1.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.1.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.1.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.1.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.2 | 0 | Main Mechanical Works | 0 | 0
C.2.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.2.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.2.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.2.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.2.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.3 | 0 | Main Electrical Works | 0 | 0
C.3.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.3.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.3.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.3.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.3.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.4 | 0 | Piping | 0 | 0
C.4.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.4.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.4.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.4.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.4.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.5 | 0 | Other civil Structure | 0 | 0
C.5.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.5.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.5.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.5.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.5.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
D | Procurement and Installation of long-lead equipment and major process items | Procurement and Installation of long-lead equipment and major process items | 0 | 0
D.1 | 0 | Procurement plan and list of sub-work packages | 0 | 0
D.1.1 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Details of proposed procurement plan
D.1.2 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Supplier detail
D.1.3 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Installation and testing
D.1.4 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Warantty and defect liability
D.1.5 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Feasibility of procurement methodology
D.1.6 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Added value to the Client
D.2 | 0 | Delivery, storage, logistics and materials management plan. | 0 | 0
D.2.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Storage plan on site
D.2.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Losgistic plan
D.3 | 0 | Equipment list | 0 | 0
D.3.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Testing schedule
D.3.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | FAT
D.3.3 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Feasibility of installation method
D.4 | 0 | Service support | 0 | 0
D.4.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Availability of local service support
D.4.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Responsibility of local service support
E | Capacity (Personal & Resources) | Capacity (Personal & Resources) | 0 | 0
E.1 | 0 | Organizational chart | 0 | 0
E.1.1 | Capacity (Personal & Resources) |  | 0 | Overal organization chart | 1 | 2022-12-20 | The Org Chart is unclear | [5 empty] | 1
E.1.2 | Capacity (Personal & Resources) |  | 0 | Functional linkage of the chart | 2 | 2022-12-20 | Linkage are unclear and cannot be justified | [5 empty] | 2
E.2 | 0 | Key team members | 0 | 0
E.2.1 | Capacity (Personal & Resources) | PM | 0 | Availability and commitment | 3 | 2022-12-20 | The asssigned PM currently holds all project management under DMCI | [5 empty] | 3
E.2.2 | Capacity (Personal & Resources) | PM | 15 | Total Experience (15 years) | 4 | 2022-12-20 | More than 20 years experiencing, involving in big projects | [5 empty] | 4
E.2.3 | Capacity (Personal & Resources) | PM | 10 | Similar experience (10 years) | 4 | 2022-12-20 | Has been able to be involved in Water Industry Projects such as pump stations and WTPs (Biggest: 1334 MLD) | [5 empty] | 4
E.2.4 | Capacity (Personal & Resources) | Project Controller | 0 | Availability and commitment | 3 | 2022-12-20 | May have availability conflict on current projects | [5 empty] | 3
E.2.5 | Capacity (Personal & Resources) | Project Controller | 10 | Total Experience of the PM (10 years) | 5 | 2022-12-20 | Has 14 years of experience mostly on water industry projects | [5 empty] | 5
E.2.6 | Capacity (Personal & Resources) | Project Controller | 5 | Similar experience of the PM (5 years) | 5 | 2022-12-20 | Achieve requirements of Manila Water for Project Controller | [5 empty] | 5
E.2.7 | Capacity (Personal & Resources) | Safety Manager | 0 | Availability and commitment | 2 | 2022-12-20 | Have recently started projects that may affect availability to project | [5 empty] | 2
E.2.8 | Capacity (Personal & Resources) | Safety Manager | 5 | Total Experience of the PM (10 years) | 4 | 2022-12-20 | 15 years of experience varying from different water industry projects. | [5 empty] | 4
E.2.9 | Capacity (Personal & Resources) | Safety Manager | 3 | Similar experience of the PM (5 years) | 5 | 2022-12-20 | Achieve requirements of Manila Water for Safety Manager | [5 empty] | 5
E.2.10 | Capacity (Personal & Resources) | Contract Administrator | 0 | Availability and commitment | 4 | 2022-12-20 | Multiple current projects may afffect availability | [5 empty] | 4
E.2.11 | Capacity (Personal & Resources) | Contract Administrator | 10 | Total experience | 5 | 2022-12-20 | more than 10 years of experience | [5 empty] | 5
E.2.12 | Capacity (Personal & Resources) | Contract Administrator | 5 | Similar experience | 4 | 2022-12-20 | exceeded minimum requirements for contract administrator | [5 empty] | 4
E.2.13 | Capacity (Personal & Resources) | Admin assistant Staff | 0 | Availability and commitment | 3 | 2022-12-20 | Currently Holds multiple projects affecting availability | [5 empty] | 3
E.2.14 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Total experience | 5 | 2022-12-20 | Has exactly 5 years experience involving on big projects including water industry | [5 empty] | 5
E.2.15 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Similar experience | 5 | 2022-12-20 | Exceeded minimum requirements for admin staff | [5 empty] | 5
E.2.16 | Capacity (Personal & Resources) | Quality manager | 0 | Availability and commitment | 5 | 2022-12-20 | Availability is less of a concern | [5 empty] | 5
E.2.17 | Capacity (Personal & Resources) | Quality manager | 10 | Total experience | 5 | 2022-12-20 | Has 23 yeears of experience in big projects | [5 empty] | 5
E.2.18 | Capacity (Personal & Resources) | Quality manager | 5 | Similar experience | 2 | 2022-12-20 | Does not have any experience in water industry projects | [5 empty] | 2
E.2.19 | Capacity (Personal & Resources) | Design manager | 0 | Availability and commitment | 3 | 2022-12-20 | Concern on availability since she currently holds all project involving design | [5 empty] | 3
E.2.20 | Capacity (Personal & Resources) | Design manager | 10 | Total experience | 5 | 2022-12-20 | Has 27 years of experience in design and build projects including water industry construction | [5 empty] | 5
E.2.21 | Capacity (Personal & Resources) | Design manager | 5 | Similar experience | 4 | 2022-12-20 | Has enough experience on water industry construction main pumphouse and WTP Rehabilitation | [5 empty] | 4
E.2.22 | Capacity (Personal & Resources) | Licensed structural engineer | 0 | Availability and commitment | 1 | 2022-12-20 | Availability is a concern since the staff has more than 5 on going projects | Is Mr. Ubay would still be fit to work on field? |  |  |  |  | 1
E.2.23 | Capacity (Personal & Resources) | Licensed structural engineer | 10 | Total experience | 5 | 2022-12-20 | Has 55 Years of Experience | [5 empty] | 5
E.2.24 | Capacity (Personal & Resources) | Licensed structural engineer | 5 | Similar experience | 4 | 2022-12-20 | Most water industry related projects are in STP and few WTPs. No details were indicated | [5 empty] | 4
E.2.25 | Capacity (Personal & Resources) | Hydraulic engineer | 0 | Availability and commitment | 3 | 2022-12-20 | Acting consultant for DMCI | [5 empty] | 3
E.2.26 | Capacity (Personal & Resources) | Hydraulic engineer | 10 | Total experience | 5 | 2022-12-20 | 40 years experience mostly related to water industry projects abroad | [5 empty] | 5
E.2.27 | Capacity (Personal & Resources) | Hydraulic engineer | 5 | Similar experience | 4 | 2022-12-20 | Most of the projects are STP and few WTPs outside the Country. | [5 empty] | 4
E.2.28 | Capacity (Personal & Resources) | Licensed mech engineer | 0 | Availability and commitment | 2 | 2022-12-20 | Has new projects on hand that might affect commitment since focus will be greatly affected | [5 empty] | 2
E.2.29 | Capacity (Personal & Resources) | Licensed mech engineer | 10 | Total experience | 5 | 2022-12-20 | Has 10 years of experience on various type of construction projects | [5 empty] | 5
E.2.30 | Capacity (Personal & Resources) | Licensed mech engineer | 5 | Similar experience | 4 | 2022-12-20 | Met necessary requirements for licensed MECH engineer set by manila water | [5 empty] | 4
E.2.31 | Capacity (Personal & Resources) | Licensed elec engineer | 0 | Availability and commitment | 4 | 2022-12-20 | Availability is less of a concern | [5 empty] | 4
E.2.32 | Capacity (Personal & Resources) | Licensed elec engineer | 10 | Total experience | 4 | 2022-12-20 | 12 years of experience in the construction industry | [5 empty] | 4
E.2.33 | Capacity (Personal & Resources) | Licensed elec engineer | 5 | Similar experience | 4 | 2022-12-20 | Met necessary requirements for licensed ELEC engineer set by manila water | [5 empty] | 4
E.2.34 | Capacity (Personal & Resources) | A&I engineer | 0 | Availability and commitment | 4 | 2022-12-20 | Availability is less of a concern | [5 empty] | 4
E.2.35 | Capacity (Personal & Resources) | A&I engineer | 10 | Total experience | 5 | 2022-12-20 | 30 years of experience in the construction industry | [5 empty] | 5
E.2.36 | Capacity (Personal & Resources) | A&I engineer | 5 | Similar experience | 5 | 2022-12-20 | Met necessary requirements for licensed A&I engineer set by manila water | [5 empty] | 5
E.2.37 | Capacity (Personal & Resources) | Construction Manager | 0 | Availability and commitment | 4 | 2022-12-20 | Availability can be slightly compromised by projects handled | [5 empty] | 4
E.2.38 | Capacity (Personal & Resources) | Construction Manager | 10 | Total experience | 4 | 2022-12-20 | more than 15 years of experience | [5 empty] | 4
E.2.39 | Capacity (Personal & Resources) | Construction Manager | 5 | Similar experience | 5 | 2022-12-20 | Involved in multiple water industry construction projects and met necessary requirements for construction manager | [5 empty] | 5
E.2.40 | Capacity (Personal & Resources) | Commissioning manager | 0 | Availability and commitment | 4 | 2022-12-20 | Availability can be slightly compromised by projects handled | [5 empty] | 4
E.2.41 | Capacity (Personal & Resources) | Commissioning manager | 10 | Total experience | 5 | 2022-12-20 | 30 years of experience in the construction industry | [5 empty] | 5
E.2.42 | Capacity (Personal & Resources) | Commissioning manager | 5 | Similar experience | 5 | 2022-12-20 | Has relevant experience in raw water intake, pump stations, and WTP projects | [5 empty] | 5
E.2.43 | Capacity (Personal & Resources) | Procurement manager | 0 | Availability and commitment | 4 | 2022-12-20 | Availability is less of a concern | [5 empty] | 4
E.2.44 | Capacity (Personal & Resources) | Procurement manager | 10 | Total experience | 5 | 2022-12-20 | 30 years of experience related to procurement management | [5 empty] | 5
E.2.45 | Capacity (Personal & Resources) | Procurement manager | 5 | Similar experience | 5 | 2022-12-20 | Currently holds projects of DMCI involving water industry construction projects | [5 empty] | 5
E.2.46 | Capacity (Personal & Resources) | Planner/Scheduler | 0 | Availability and commitment | 4 | 2022-12-20 | Availability is less of a concern | [5 empty] | 4
E.2.47 | Capacity (Personal & Resources) | Planner/Scheduler | 5 | Total experience | 5 | 2022-12-20 | 14 years of experience from different kind of construction projects | [5 empty] | 5
E.2.48 | Capacity (Personal & Resources) | Planner/Scheduler | 3 | Similar experience | 5 | 2022-12-20 | Has relevant experience in raw water intake, pump stations, and WTP projects | [5 empty] | 5
E.3 | Certifications on quality, safety and occupational health program | Certifications on quality, safety and occupational health program | 0 | 0
E.3.1 | Certifications on quality, safety and occupational health program |  | 0 | Certification on quality | 5 | 2022-12-20 | Certificate is presented | [5 empty] | 5
E.3.2 | Certifications on quality, safety and occupational health program |  | 0 | Certification on safety | 5 | 2022-12-20 | Certificate is presented | [5 empty] | 5
E.3.3 | Certifications on quality, safety and occupational health program |  | 0 | Certification on OHP | 5 | 2022-12-20 | Certificate is presented | [5 empty] | 5
E.4 | Training plan | Training plan | 0 | 0
E.4.1 | Training plan |  | 0 | Written eviden | 5 | 2022-12-20 | Documents are presented | [5 empty] | 5
E.4.2 | Training plan |  | 0 | Training plan and schedule | 5 | 2022-12-20 | Training plan is astoundingly given and documented | [5 empty] | 5
E.4.3 | Training plan |  | 0 | Knowledge transfer workshop | 5 | 2022-12-20 | Meets objectives | [5 empty] | 5
E.5 | Equipment information | Construction Equipment Information | 0 | 0
E.5.1 | Equipment information |  | 0 | Sourcing | 5 | 2022-12-20 | Complete Documents | [5 empty] | 5
E.5.2 | Equipment information |  | 0 | Efficiency | 5 | 2022-12-20 | Complete certifications and testing | [5 empty] | 5
E.5.3 | Equipment information |  | 0 | Availability | 5 | 2022-12-20 | Schedules are detailed | [5 empty] | 5
E.5.4 | Equipment information |  | 0 | Reliability | 5 | 2022-12-20 | Reassurance papers and certificates qualifying to reliability are presented | [5 empty] | 5
E.6 | Construction & Installation Manpower | Construction & Installation Manpower | 0 | 0
E.6.1 | Construction & Installation Manpower |  | 0 | Construction manpower | 5 | 2022-12-20 | Well organized | [5 empty] | 5
E.6.2 | Construction & Installation Manpower |  | 0 | Installation manpower | 5 | 2022-12-20 | Well organized | [5 empty] | 5

## FirstBalfour
FIRSTBALFOUR
ID | Hierachy levels |  |  |  | First Time Assessment |  |  |  | Second Assessment
ID | Level 1 | Level 2 | Level 3 | Level 4 | Score | Score Date | Narrative | Clarification Note | Answer from Bidder | Answered date | Score | Score Date | Final_Score
Total
A | Delivery Plan | 0 | 0 | 0
A.1 | Detailed WBS with schedule and S-curve | 0 | 0 | 0
A.1.1 | Detailed WBS with schedule and S-curve | 0 | 0 | Bidder to follow the WBS defined in ER
A.1.2 | Detailed WBS with schedule and S-curve | 0 | 0 | Sufficiency and completeness of the WBS
A.1.3 | Detailed WBS with schedule and S-curve | 0 | 0 | Schedule is given in required format
A.1.4 | Detailed WBS with schedule and S-curve | 0 | 0 | Interim milestones
A.1.5 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of milestones
A.1.6 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of linkages
A.1.7 | Detailed WBS with schedule and S-curve | 0 | 0 | Consistency with delivery narrative and methodological approach
A.1.8 | Detailed WBS with schedule and S-curve | 0 | 0 | Critical path is highlighted in the schedule program
A.1.9 | Detailed WBS with schedule and S-curve | 0 | 0 | Resources allocation
A.1.10 | Detailed WBS with schedule and S-curve | 0 | 0 | S-curve is probably drawn in the schedule program
A.2 | Delivery Narrative | 0 | 0 | 0
A.2.1 | Delivery Narrative | 0 | 0 | Understanding of the works
A.2.2 | Delivery Narrative | 0 | 0 | Well written and demonstration of approach and delivery of the project
A.2.3 | Delivery Narrative | 0 | 0 | Key activities and deliverables
A.2.4 | Delivery Narrative | 0 | 0 | Feasibility of the approach
A.2.5 | Delivery Narrative | 0 | 0 | Constraints involved with the approach
A.2.6 | Delivery Narrative | 0 | 0 | Resources allocation are persuative and feasible
A.2.7 | Delivery Narrative | 0 | 0 | Advantage of offerred contract strategy
A.2.8 | Delivery Narrative | 0 | 0 | Linkage to deliverable plan (above)
A.2.9 | Delivery Narrative | 0 | 0 | Added value to the Client
A.3 | Safety Plan | 0 | 0 | 0
A.3.1 | Safety Plan | 0 | 0 | Overall Safety Plan
A.3.2 | Safety Plan | 0 | 0 | Safety personnel
A.3.3 | Safety Plan | 0 | 0 | Safety plan for each WP, particularly for critical work items
A.3.4 | Safety Plan | 0 | 0 | Demonstration of historical records, data on safety of previous projects
A.3.5 | Safety Plan | 0 | 0 | Safety compliance to Client's requirement
A.3.6 | Safety Plan | 0 | 0 | Safety compliance to local authority
A.3.7 | Safety Plan | 0 | 0 | Evacuation and immediate actions to follow when safety incident occurs
A.4 | Risk Management Plan (including contingency plan) | 0 | 0 | 0
A.4.1 | Risk Management Plan (including contingency plan) | 0 | 0 | Overall risk management plan
A.4.2 | Risk Management Plan (including contingency plan) | 0 | 0 | Specific risk plan for critical work
A.4.3 | Risk Management Plan (including contingency plan) | 0 | 0 | Understanding risks, particularly during execution on critical items
A.4.4 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk assessment methodology
A.4.5 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk management register and tool
A.4.6 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk removal, reduction, and mitigation plan
A.4.7 | Risk Management Plan (including contingency plan) | 0 | 0 | Feasibility of the overal risk plan
A.5 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | 0
A.5.1 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Completeness of deliverables in tabular format
A.5.2 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Linkage of deliverables to detailed schedule
A.5.3 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Feasibility of the deliverable plan
B | Design | 0 | 0 | 0
B.1 | 0 | M&E | 0 | 0
B.1.1 | Design | M&E | General | QA/QC
B.1.2 | Design | M&E | General | Deliverable Plan
B.1.3 | Design | M&E | General | Value Engineering
B.1.4 | Design | M&E | General | Resource Plan
B.1.5 | Design | M&E | General | Risk and safety in design
B.1.6 | Design | M&E | Intake Chamber | Feasibility
B.1.7 | Design | M&E | Intake Chamber | Constructability
B.1.8 | Design | M&E | Intake Chamber | Correctness
B.1.9 | Design | M&E | Outside Intake Chamber | Feasibility
B.1.10 | Design | M&E | Outside Intake Chamber | Constructability
B.1.11 | Design | M&E | Outside Intake Chamber | Correctness
B.2 | 0 | Automation and Instrumentation (A&I) | 0 | 0
B.2.1 | Design | Automation and Instrumentation (A&I) | General | QA/QC
B.2.2 | Design | Automation and Instrumentation (A&I) | General | Deliverable Plan
B.2.3 | Design | Automation and Instrumentation (A&I) | General | Value Engineering
B.2.4 | Design | Automation and Instrumentation (A&I) | General | Resource Plan
B.2.5 | Design | Automation and Instrumentation (A&I) | General | Risk and safety in design
B.2.6 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Feasibility
B.2.7 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Constructability
B.2.8 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Correctness
B.2.9 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Feasibility
B.2.10 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Constructability
B.2.11 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Correctness
B.3 | 0 | Hydraulics and others | 0 | 0
B.3.1 | Design | Hydraulics and others | General | QA/QC
B.3.2 | Design | Hydraulics and others | General | Deliverable Plan
B.3.3 | Design | Hydraulics and others | General | Value Engineering
B.3.4 | Design | Hydraulics and others | General | Resource Plan
B.3.5 | Design | Hydraulics and others | General | Risk and safety in design
B.3.6 | Design | Hydraulics and others | Intake Chamber | Feasibility
B.3.7 | Design | Hydraulics and others | Intake Chamber | Constructability
B.3.8 | Design | Hydraulics and others | Intake Chamber | Correctness
B.3.9 | Design | Hydraulics and others | Outside Intake Chamber | Feasibility
B.3.10 | Design | Hydraulics and others | Outside Intake Chamber | Constructability
B.3.11 | Design | Hydraulics and others | Outside Intake Chamber | Correctness
B.4 | 0 | Civil/structural design | 0 | 0
B.4.1 | Design | Civil/structural design | General | QA/QC
B.4.2 | Design | 0 | General | Deliverable Plan
B.4.3 | Design | 0 | General | Value Engineering
B.4.4 | Design | 0 | General | Resource Plan
B.4.5 | Design | 0 | General | Risk and safety in design
B.4.6 | Design | 0 | Intake Chamber | Feasibility
B.4.7 | Design | 0 | Intake Chamber | Constructability
B.4.8 | Design | 0 | Intake Chamber | Correctness
B.4.9 | Design | 0 | Outside Intake Chamber | Feasibility
B.4.10 | Design | 0 | Outside Intake Chamber | Constructability
B.4.11 | Design | 0 | Outside Intake Chamber | Correctness
C | Construction/Installation Program and methodology | 0 | 0 | 0
C.1 | 0 | Control System, Automation & Instrumentation | 0 | 0
C.1.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.1.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.1.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.1.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.1.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.2 | 0 | Main Mechanical Works | 0 | 0
C.2.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.2.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.2.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.2.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.2.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.3 | 0 | Main Electrical Works | 0 | 0
C.3.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.3.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.3.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.3.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.3.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.4 | 0 | Piping | 0 | 0
C.4.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.4.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.4.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.4.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.4.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.5 | 0 | Other civil Structure | 0 | 0
C.5.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.5.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.5.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.5.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.5.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
D | Procurement and Installation of long-lead equipment and major process items | Procurement and Installation of long-lead equipment and major process items | 0 | 0
D.1 | 0 | Procurement plan and list of sub-work packages | 0 | 0
D.1.1 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Details of proposed procurement plan
D.1.2 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Supplier detail
D.1.3 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Installation and testing
D.1.4 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Warantty and defect liability
D.1.5 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Feasibility of procurement methodology
D.1.6 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Added value to the Client
D.2 | 0 | Delivery, storage, logistics and materials management plan. | 0 | 0
D.2.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Storage plan on site
D.2.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Losgistic plan
D.3 | 0 | Equipment list | 0 | 0
D.3.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Testing schedule
D.3.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | FAT
D.3.3 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Feasibility of installation method
D.4 | 0 | Service support | 0 | 0
D.4.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Availability of local service support
D.4.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Responsibility of local service support
E | Capacity (Personal & Resources) | Capacity (Personal & Resources) | 0 | 0
E.1 | 0 | Organizational chart | 0 | 0
E.1.1 | Capacity (Personal & Resources) |  | 0 | Overal organization chart | 5 | 2022-12-21 | Org chart is clear enough to understand and well constructed | [5 empty] | 5
E.1.2 | Capacity (Personal & Resources) |  | 0 | Functional linkage of the chart | 5 | 2022-12-21 | Its linkage are very reasonable and shows efficiency between groups in the org chart | [5 empty] | 5
E.2 | 0 | Key team members | 0 | 0
E.2.1 | Capacity (Personal & Resources) | PM | 0 | Availability and commitment | 3 | 2022-12-21 | Has ongoing big projects as of 2019 to present | [5 empty] | 3
E.2.2 | Capacity (Personal & Resources) | PM | 15 | Total Experience (15 years) | 5 | 2022-12-21 | Has 30 years of experience | [5 empty] | 5
E.2.3 | Capacity (Personal & Resources) | PM | 10 | Similar experience (10 years) | 4 | 2022-12-21 | Experience were mostly from tunneling and huge construction project | [5 empty] | 4
E.2.4 | Capacity (Personal & Resources) | Project Controller | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is slight of a concern | [5 empty] | 4
E.2.5 | Capacity (Personal & Resources) | Project Controller | 10 | Total Experience of the PM (10 years) | 4 | 2022-12-21 | has 11 years of profesional experience | [5 empty] | 4
E.2.6 | Capacity (Personal & Resources) | Project Controller | 5 | Similar experience of the PM (5 years) | 1 | 2022-12-21 | Most of expreience are in Energy sector and bridges | [5 empty] | 1
E.2.7 | Capacity (Personal & Resources) | Safety Manager | 0 | Availability and commitment | 3 | 2022-12-21 | Has current ongoing projects that might affect availability | [5 empty] | 3
E.2.8 | Capacity (Personal & Resources) | Safety Manager | 5 | Total Experience of the PM (10 years) | 4 | 2022-12-21 | Has 12 years of experience on various industries as a safety engineer, manager, and officer | [5 empty] | 4
E.2.9 | Capacity (Personal & Resources) | Safety Manager | 3 | Similar experience of the PM (5 years) | 3 | 2022-12-21 | Has experience only in tunneling on water industry construction projects | [5 empty] | 3
E.2.10 | Capacity (Personal & Resources) | Contract Administrator | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is slight of a concern since the contract admin. Has a currently new project managing as of 2022 | [5 empty] | 4
E.2.11 | Capacity (Personal & Resources) | Contract Administrator | 10 | Total experience | 4 | 2022-12-21 | Has more than 18 years of expereience but mostly on highrise building construction | [5 empty] | 4
E.2.12 | Capacity (Personal & Resources) | Contract Administrator | 5 | Similar experience | 3 | 2022-12-21 | Involved in major construction projects costing more than 100 M Pesos to construct however, no relevant experience with regards to the nature of work of client | [5 empty] | 3
E.2.13 | Capacity (Personal & Resources) | Admin assistant Staff | 0 | Availability and commitment | 4 | 2022-12-21 | Currently handles a project that may affect availability. It will be a concern since admi assistant will be the one coordinating with the client | [5 empty] | 4
E.2.14 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Total experience | 4 | 2022-12-21 | Has 26 years of experience to high scale construction projects | [5 empty] | 4
E.2.15 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Similar experience | 4 | 2022-12-21 | Has 11 years of relevant experience in water industry construction projects | [5 empty] | 4
E.2.16 | Capacity (Personal & Resources) | Quality manager | 0 | Availability and commitment | 3 | 2022-12-21 | Availability may be a concern since quality manager is currently holding a big water industry construction project. | [5 empty] | 3
E.2.17 | Capacity (Personal & Resources) | Quality manager | 10 | Total experience | 5 | 2022-12-21 | has 41 years of relevant experience varying from water and energy sector project | [5 empty] | 5
E.2.18 | Capacity (Personal & Resources) | Quality manager | 5 | Similar experience | 5 | 2022-12-21 | has experience on quality management in multiple water construction projects and has been involved in design and build in eastbay phase 1 WTP | [5 empty] | 5
E.2.19 | Capacity (Personal & Resources) | Design manager | 0 | Availability and commitment | 4 | 2022-12-21 | Availability and commitment would be slight of a concern since currently has 1 ongoing major project | [5 empty] | 4
E.2.20 | Capacity (Personal & Resources) | Design manager | 10 | Total experience | 4 | 2022-12-21 | Has 31 years of experience mostly on water construction related projects | [5 empty] | 4
E.2.21 | Capacity (Personal & Resources) | Design manager | 5 | Similar experience | 3 | 2022-12-21 | Has relevant experience in water project design but does not meet yet meet standards client is looking for. (Atleast 70% of the requirements are met) | [5 empty] | 3
E.2.22 | Capacity (Personal & Resources) | Licensed structural engineer | 0 | Availability and commitment | 3 | 2022-12-21 | Currently holds a big project that might affect availability | [5 empty] | 3
E.2.23 | Capacity (Personal & Resources) | Licensed structural engineer | 10 | Total experience | 4 | 2022-12-21 | Has 51 years of experience in construction, mainly exposed to high scale constrcution projects. | [5 empty] | 4
E.2.24 | Capacity (Personal & Resources) | Licensed structural engineer | 5 | Similar experience | 4 | 2022-12-21 | Current Relevant experience were mostly related to high-way construction and large scale highway bridges. Experience in major water projects are way back 2006 | [5 empty] | 4
E.2.25 | Capacity (Personal & Resources) | Hydraulic engineer | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is less of a concern | [5 empty] | 4
E.2.26 | Capacity (Personal & Resources) | Hydraulic engineer | 10 | Total experience | 5 | 2022-12-21 | Has 37 years of experience mostly on water industry construction | [5 empty] | 5
E.2.27 | Capacity (Personal & Resources) | Hydraulic engineer | 5 | Similar experience | 5 | 2022-12-21 | Able to achieve requirements of client | [5 empty] | 5
E.2.28 | Capacity (Personal & Resources) | Licensed mech engineer | 0 | Availability and commitment | 5 | 2022-12-21 | Currently acting as a PME Consultant | [5 empty] | 5
E.2.29 | Capacity (Personal & Resources) | Licensed mech engineer | 10 | Total experience | 5 | 2022-12-21 | has 45 years of experience mostly in water industry sector | [5 empty] | 5
E.2.30 | Capacity (Personal & Resources) | Licensed mech engineer | 5 | Similar experience | 5 | 2022-12-21 | Has been employed in Manila water. Hence, exposure to relevant experience is high | [5 empty] | 5
E.2.31 | Capacity (Personal & Resources) | Licensed elec engineer | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is less of a concern | [5 empty] | 4
E.2.32 | Capacity (Personal & Resources) | Licensed elec engineer | 10 | Total experience | 4 | 2022-12-21 | Has 22 years of experience mostly on water projects | [5 empty] | 4
E.2.33 | Capacity (Personal & Resources) | Licensed elec engineer | 5 | Similar experience | 3 | 2022-12-21 | Able to meet some requirements clients looking for current projects are provincial water supply for infrastructure | [5 empty] | 3
E.2.34 | Capacity (Personal & Resources) | A&I engineer | 0 | Availability and commitment | 1 | 2022-12-21 | Has 6 ongoing managing projects and this may affect availability and commitment | [5 empty] | 1
E.2.35 | Capacity (Personal & Resources) | A&I engineer | 10 | Total experience | 4 | 2022-12-21 | Has 20 years of experience in construction industry but on a few for water sector | [5 empty] | 4
E.2.36 | Capacity (Personal & Resources) | A&I engineer | 5 | Similar experience | 4 | 2022-12-21 | Most experience are in wastewater followed by WTP construction | [5 empty] | 4
E.2.37 | Capacity (Personal & Resources) | Construction Manager | 0 | Availability and commitment | 4 | 2022-12-21 | Currently holding design and build of East Bay WTP Phase 1 Project. May affect Availability slightly | [5 empty] | 4
E.2.38 | Capacity (Personal & Resources) | Construction Manager | 10 | Total experience | 4 | 2022-12-21 | Has 19 years of experience and has been involved in large scale infrastructure projects both local and international | [5 empty] | 4
E.2.39 | Capacity (Personal & Resources) | Construction Manager | 5 | Similar experience | 4 | 2022-12-21 | Has 10 years experience in water industry construction projects. Also includes current projects of client. However, past experiences were mostly related to manufacturing plant construction projects. | [5 empty] | 4
E.2.40 | Capacity (Personal & Resources) | Commissioning manager | 0 | Availability and commitment | 4 | 2022-12-21 | Acting as consultant for the bidder | [5 empty] | 4
E.2.41 | Capacity (Personal & Resources) | Commissioning manager | 10 | Total experience | 5 | 2022-12-21 | Has 31 years of experience almost all of the exposure are related to water construction projects (smallscale - largescale projects) | [5 empty] | 5
E.2.42 | Capacity (Personal & Resources) | Commissioning manager | 5 | Similar experience | 5 | 2022-12-21 | Has exceeded client requirements for a staff at commissioning manager | [5 empty] | 5
E.2.43 | Capacity (Personal & Resources) | Procurement manager | 0 | Availability and commitment | 4 | 2022-12-21 | Has an ongoing project which would slightly affect availability | [5 empty] | 4
E.2.44 | Capacity (Personal & Resources) | Procurement manager | 10 | Total experience | 3 | 2022-12-21 | Has 12 years of experience on various industries as a procurment manager of different projects handled | [5 empty] | 3
E.2.45 | Capacity (Personal & Resources) | Procurement manager | 5 | Similar experience | 3 | 2022-12-21 | Experience does not yet meet requirement of Client but has relevant experience on water projects | [5 empty] | 3
E.2.46 | Capacity (Personal & Resources) | Planner/Scheduler | 0 | Availability and commitment | 4 | 2022-12-21 | Availability may be a slight concern as project progress | [5 empty] | 4
E.2.47 | Capacity (Personal & Resources) | Planner/Scheduler | 5 | Total experience | 4 | 2022-12-21 | has 7 years of experience in construction project act as a planning engineer | [5 empty] | 4
E.2.48 | Capacity (Personal & Resources) | Planner/Scheduler | 3 | Similar experience | 5 | 2022-12-21 | Able to exceed needed requirements of client and has experience on water construction projects | [5 empty] | 5
E.3 | Certifications on quality, safety and occupational health program | Certifications on quality, safety and occupational health program | 0 | 0
E.3.1 | Certifications on quality, safety and occupational health program |  | 0 | Certification on quality | 1 | 2022-12-21 | No present certification on quality management but key members has trainings and courses related QM. | [5 empty] | 1
E.3.2 | Certifications on quality, safety and occupational health program |  | 0 | Certification on safety | 1 | 2022-12-21 | Does not have any presented certificate on safety. But some of its keymembers conducted OSH trainings and H&S Practice course | [5 empty] | 1
E.3.3 | Certifications on quality, safety and occupational health program |  | 0 | Certification on OHP | 5 | 2022-12-21 | Able to provide a certificate for OHP | [5 empty] | 5
E.4 | Training plan | Training plan | 0 | 0
E.4.1 | Training plan |  | 0 | Written eviden | 5 | 2022-12-21 | Able to present evidence of conduction of trainings | [5 empty] | 5
E.4.2 | Training plan |  | 0 | Training plan and schedule | 5 | 2022-12-21 | Has presented curriculum of training plan to all human resource to be required | [5 empty] | 5
E.4.3 | Training plan |  | 0 | Knowledge transfer workshop | 5 | 2022-12-21 | Has specific programs related to leadership programs for all working members | [5 empty] | 5
E.5 | Equipment information | Construction Equipment Information | 0 | 0
E.5.1 | Equipment information |  | 0 | Sourcing | 5 | 2022-12-21 | Bidder has an outsource for equipment which is T1. Furthermore, equipment needed on the project is complete | [5 empty] | 5
E.5.2 | Equipment information |  | 0 | Efficiency | 5 | 2022-12-21 | Therma 1 transports promotes standardized and tested equipments for all of the items to be used by clients | [5 empty] | 5
E.5.3 | Equipment information |  | 0 | Availability | 5 | 2022-12-21 | Availability will not be a concern since equipment are outsourced. | [5 empty] | 5
E.5.4 | Equipment information |  | 0 | Reliability | 5 | 2022-12-21 | Therma 1 transports are one of the major providers of heavy equipments in the country | [5 empty] | 5
E.6 | Construction & Installation Manpower | Construction & Installation Manpower | 0 | 0
E.6.1 | Construction & Installation Manpower |  | 0 | Construction manpower | 4 | 2022-12-21 | Number of manpower is adequate for the project and comparable to other bidders (Averaging with other bidders) | [5 empty] | 4
E.6.2 | Construction & Installation Manpower |  | 0 | Installation manpower | 3 | 2022-12-21 | some Equipment operators are probably outsourced from the partnered equipment provider and this would affect coordination | [5 empty] | 3

## MEC
MEC
ID | Hierachy levels |  |  |  | First Time Assessment |  |  |  | Second Assessment
ID | Level 1 | Level 2 | Level 3 | Level 4 | Score | Score Date | Narrative | Clarification Note | Answer from Bidder | Answered date | Score | Score Date | Final_Score
Total
A | Delivery Plan | 0 | 0 | 0
A.1 | Detailed WBS with schedule and S-curve | 0 | 0 | 0
A.1.1 | Detailed WBS with schedule and S-curve | 0 | 0 | Bidder to follow the WBS defined in ER
A.1.2 | Detailed WBS with schedule and S-curve | 0 | 0 | Sufficiency and completeness of the WBS
A.1.3 | Detailed WBS with schedule and S-curve | 0 | 0 | Schedule is given in required format
A.1.4 | Detailed WBS with schedule and S-curve | 0 | 0 | Interim milestones
A.1.5 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of milestones
A.1.6 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of linkages
A.1.7 | Detailed WBS with schedule and S-curve | 0 | 0 | Consistency with delivery narrative and methodological approach
A.1.8 | Detailed WBS with schedule and S-curve | 0 | 0 | Critical path is highlighted in the schedule program
A.1.9 | Detailed WBS with schedule and S-curve | 0 | 0 | Resources allocation
A.1.10 | Detailed WBS with schedule and S-curve | 0 | 0 | S-curve is probably drawn in the schedule program
A.2 | Delivery Narrative | 0 | 0 | 0
A.2.1 | Delivery Narrative | 0 | 0 | Understanding of the works
A.2.2 | Delivery Narrative | 0 | 0 | Well written and demonstration of approach and delivery of the project
A.2.3 | Delivery Narrative | 0 | 0 | Key activities and deliverables
A.2.4 | Delivery Narrative | 0 | 0 | Feasibility of the approach
A.2.5 | Delivery Narrative | 0 | 0 | Constraints involved with the approach
A.2.6 | Delivery Narrative | 0 | 0 | Resources allocation are persuative and feasible
A.2.7 | Delivery Narrative | 0 | 0 | Advantage of offerred contract strategy
A.2.8 | Delivery Narrative | 0 | 0 | Linkage to deliverable plan (above)
A.2.9 | Delivery Narrative | 0 | 0 | Added value to the Client
A.3 | Safety Plan | 0 | 0 | 0
A.3.1 | Safety Plan | 0 | 0 | Overall Safety Plan
A.3.2 | Safety Plan | 0 | 0 | Safety personnel
A.3.3 | Safety Plan | 0 | 0 | Safety plan for each WP, particularly for critical work items
A.3.4 | Safety Plan | 0 | 0 | Demonstration of historical records, data on safety of previous projects
A.3.5 | Safety Plan | 0 | 0 | Safety compliance to Client's requirement
A.3.6 | Safety Plan | 0 | 0 | Safety compliance to local authority
A.3.7 | Safety Plan | 0 | 0 | Evacuation and immediate actions to follow when safety incident occurs
A.4 | Risk Management Plan (including contingency plan) | 0 | 0 | 0
A.4.1 | Risk Management Plan (including contingency plan) | 0 | 0 | Overall risk management plan
A.4.2 | Risk Management Plan (including contingency plan) | 0 | 0 | Specific risk plan for critical work
A.4.3 | Risk Management Plan (including contingency plan) | 0 | 0 | Understanding risks, particularly during execution on critical items
A.4.4 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk assessment methodology
A.4.5 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk management register and tool
A.4.6 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk removal, reduction, and mitigation plan
A.4.7 | Risk Management Plan (including contingency plan) | 0 | 0 | Feasibility of the overal risk plan
A.5 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | 0
A.5.1 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Completeness of deliverables in tabular format
A.5.2 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Linkage of deliverables to detailed schedule
A.5.3 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Feasibility of the deliverable plan
B | Design | 0 | 0 | 0
B.1 | 0 | M&E | 0 | 0
B.1.1 | Design | M&E | General | QA/QC
B.1.2 | Design | M&E | General | Deliverable Plan
B.1.3 | Design | M&E | General | Value Engineering
B.1.4 | Design | M&E | General | Resource Plan
B.1.5 | Design | M&E | General | Risk and safety in design
B.1.6 | Design | M&E | Intake Chamber | Feasibility
B.1.7 | Design | M&E | Intake Chamber | Constructability
B.1.8 | Design | M&E | Intake Chamber | Correctness
B.1.9 | Design | M&E | Outside Intake Chamber | Feasibility
B.1.10 | Design | M&E | Outside Intake Chamber | Constructability
B.1.11 | Design | M&E | Outside Intake Chamber | Correctness
B.2 | 0 | Automation and Instrumentation (A&I) | 0 | 0
B.2.1 | Design | Automation and Instrumentation (A&I) | General | QA/QC
B.2.2 | Design | Automation and Instrumentation (A&I) | General | Deliverable Plan
B.2.3 | Design | Automation and Instrumentation (A&I) | General | Value Engineering
B.2.4 | Design | Automation and Instrumentation (A&I) | General | Resource Plan
B.2.5 | Design | Automation and Instrumentation (A&I) | General | Risk and safety in design
B.2.6 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Feasibility
B.2.7 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Constructability
B.2.8 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Correctness
B.2.9 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Feasibility
B.2.10 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Constructability
B.2.11 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Correctness
B.3 | 0 | Hydraulics and others | 0 | 0
B.3.1 | Design | Hydraulics and others | General | QA/QC
B.3.2 | Design | Hydraulics and others | General | Deliverable Plan
B.3.3 | Design | Hydraulics and others | General | Value Engineering
B.3.4 | Design | Hydraulics and others | General | Resource Plan
B.3.5 | Design | Hydraulics and others | General | Risk and safety in design
B.3.6 | Design | Hydraulics and others | Intake Chamber | Feasibility
B.3.7 | Design | Hydraulics and others | Intake Chamber | Constructability
B.3.8 | Design | Hydraulics and others | Intake Chamber | Correctness
B.3.9 | Design | Hydraulics and others | Outside Intake Chamber | Feasibility
B.3.10 | Design | Hydraulics and others | Outside Intake Chamber | Constructability
B.3.11 | Design | Hydraulics and others | Outside Intake Chamber | Correctness
B.4 | 0 | Civil/structural design | 0 | 0
B.4.1 | Design | Civil/structural design | General | QA/QC
B.4.2 | Design | 0 | General | Deliverable Plan
B.4.3 | Design | 0 | General | Value Engineering
B.4.4 | Design | 0 | General | Resource Plan
B.4.5 | Design | 0 | General | Risk and safety in design
B.4.6 | Design | 0 | Intake Chamber | Feasibility
B.4.7 | Design | 0 | Intake Chamber | Constructability
B.4.8 | Design | 0 | Intake Chamber | Correctness
B.4.9 | Design | 0 | Outside Intake Chamber | Feasibility
B.4.10 | Design | 0 | Outside Intake Chamber | Constructability
B.4.11 | Design | 0 | Outside Intake Chamber | Correctness
C | Construction/Installation Program and methodology | 0 | 0 | 0
C.1 | 0 | Control System, Automation & Instrumentation | 0 | 0
C.1.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.1.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.1.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.1.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.1.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.2 | 0 | Main Mechanical Works | 0 | 0
C.2.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.2.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.2.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.2.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.2.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.3 | 0 | Main Electrical Works | 0 | 0
C.3.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.3.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.3.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.3.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.3.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.4 | 0 | Piping | 0 | 0
C.4.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.4.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.4.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.4.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.4.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.5 | 0 | Other civil Structure | 0 | 0
C.5.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.5.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.5.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.5.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.5.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
D | Procurement and Installation of long-lead equipment and major process items | Procurement and Installation of long-lead equipment and major process items | 0 | 0
D.1 | 0 | Procurement plan and list of sub-work packages | 0 | 0
D.1.1 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Details of proposed procurement plan
D.1.2 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Supplier detail
D.1.3 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Installation and testing
D.1.4 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Warantty and defect liability
D.1.5 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Feasibility of procurement methodology
D.1.6 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Added value to the Client
D.2 | 0 | Delivery, storage, logistics and materials management plan. | 0 | 0
D.2.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Storage plan on site
D.2.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Losgistic plan
D.3 | 0 | Equipment list | 0 | 0
D.3.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Testing schedule
D.3.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | FAT
D.3.3 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Feasibility of installation method
D.4 | 0 | Service support | 0 | 0
D.4.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Availability of local service support
D.4.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Responsibility of local service support
E | Capacity (Personal & Resources) | Capacity (Personal & Resources) | 0 | 0
E.1 | 0 | Organizational chart | 0 | 0
E.1.1 | Capacity (Personal & Resources) |  | 0 | Overal organization chart | 5 | 2022-12-21 | Clear and Understandable. Well organized | [5 empty] | 5
E.1.2 | Capacity (Personal & Resources) |  | 0 | Functional linkage of the chart | 4 | 2022-12-21 | Linkage are reasonable and logical | [5 empty] | 4
E.2 | 0 | Key team members | 0 | 0
E.2.1 | Capacity (Personal & Resources) | PM | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is a slight concern | [5 empty] | 4
E.2.2 | Capacity (Personal & Resources) | PM | 15 | Total Experience (15 years) | 1 | 2022-12-21 | Does not meet requirements of Manila Water | [5 empty] | 1
E.2.3 | Capacity (Personal & Resources) | PM | 10 | Similar experience (10 years) | 2 | 2022-12-21 | Most projects involved are in Water but does not qualify in clients requirements | [5 empty] | 2
E.2.4 | Capacity (Personal & Resources) | Project Controller | 0 | Availability and commitment | 4 | 2022-12-21 | Availability may not be an issue | [5 empty] | 4
E.2.5 | Capacity (Personal & Resources) | Project Controller | 10 | Total Experience of the PM (10 years) | 3 | 2022-12-21 | 16 years of expereience mostly on medium to high rise buildings | [5 empty] | 3
E.2.6 | Capacity (Personal & Resources) | Project Controller | 5 | Similar experience of the PM (5 years) | 1 | 2022-12-21 | only a few projects were involved in water sector at the same time does not meet client requirements | [5 empty] | 1
E.2.7 | Capacity (Personal & Resources) | Safety Manager | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is less of a concern | [5 empty] | 4
E.2.8 | Capacity (Personal & Resources) | Safety Manager | 5 | Total Experience of the PM (10 years) | 5 | 2022-12-21 | Has 12 years experience as a H&S Practitioner | [5 empty] | 5
E.2.9 | Capacity (Personal & Resources) | Safety Manager | 3 | Similar experience of the PM (5 years) | 2 | 2022-12-21 | Only a few requirements were mat by the safety officer assigned | [5 empty] | 2
E.2.10 | Capacity (Personal & Resources) | Contract Administrator | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is less of a concern | [5 empty] | 4
E.2.11 | Capacity (Personal & Resources) | Contract Administrator | 10 | Total experience | 4 | 2022-12-21 | Has 29 years of experience | [5 empty] | 4
E.2.12 | Capacity (Personal & Resources) | Contract Administrator | 5 | Similar experience | 3 | 2022-12-21 | Involved relevant exposure is contract management of pipelaying works | [5 empty] | 3
E.2.13 | Capacity (Personal & Resources) | Admin assistant Staff | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is less of a concern | [5 empty] | 4
E.2.14 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Total experience | 4 | 2022-12-21 | Has 7 years of experience on large scale infrastructure projects | [5 empty] | 4
E.2.15 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Similar experience | 3 | 2022-12-21 | Most experience are related to medium to high rise infrastructure and only one current works relate to water | [5 empty] | 3
E.2.16 | Capacity (Personal & Resources) | Quality manager | 0 | Availability and commitment | 3 | 2022-12-21 | Availability is slight of a concern since has a huge role on ongoing projects of the company | [5 empty] | 3
E.2.17 | Capacity (Personal & Resources) | Quality manager | 10 | Total experience | 3 | 2022-12-21 | only has 7 years of experience in construction but mostly on water projects | [5 empty] | 3
E.2.18 | Capacity (Personal & Resources) | Quality manager | 5 | Similar experience | 4 | 2022-12-21 | Most works as quality assurance were done in water related projects | [5 empty] | 4
E.2.19 | Capacity (Personal & Resources) | Design manager | 0 | Availability and commitment | 3 | 2022-12-21 | Availability is slight of a concern since design manager is currently assignd on projects in different region in the country | [5 empty] | 3
E.2.20 | Capacity (Personal & Resources) | Design manager | 10 | Total experience | 5 | 2022-12-21 | 28 years of experience most of which are related to water projects | [5 empty] | 5
E.2.21 | Capacity (Personal & Resources) | Design manager | 5 | Similar experience | 5 | 2022-12-21 | has 22 years of relevant experience and met the requirements of client as for a design manager | [5 empty] | 5
E.2.22 | Capacity (Personal & Resources) | Licensed structural engineer | 0 | Availability and commitment | 3 | 2022-12-21 | Has 2 projects involved that may affect commitment and availability | [5 empty] | 3
E.2.23 | Capacity (Personal & Resources) | Licensed structural engineer | 10 | Total experience | 3 | 2022-12-21 | Only has 9 years of experience in the construction most of which are in STP design and build | [5 empty] | 3
E.2.24 | Capacity (Personal & Resources) | Licensed structural engineer | 5 | Similar experience | 3 | 2022-12-21 | Experience were mostly focused on design and construction of STP | [5 empty] | 3
E.2.25 | Capacity (Personal & Resources) | Hydraulic engineer | 0 | Availability and commitment | 3 | 2022-12-21 | Availability is a slight concern since it carries multiple tasks in their company | [5 empty] | 3
E.2.26 | Capacity (Personal & Resources) | Hydraulic engineer | 10 | Total experience | 3 | 2022-12-21 | Has 10 years of experience in the industry | [5 empty] | 3
E.2.27 | Capacity (Personal & Resources) | Hydraulic engineer | 5 | Similar experience | 4 | 2022-12-21 | All experience are tackled in water projects but not yet meeting exact requirements of client (atleast 80-90% achieved) | [5 empty] | 4
E.2.28 | Capacity (Personal & Resources) | Licensed mech engineer | 0 | Availability and commitment | 1 | 2022-12-21 | Most of the projects handled are still in progress availability and commitment is a concern | please recheck CV if this is update since employement record is not properly recorded |  |  |  |  | 1
E.2.29 | Capacity (Personal & Resources) | Licensed mech engineer | 10 | Total experience | 4 | 2022-12-21 | Has 16 years of experience in construction | [5 empty] | 4
E.2.30 | Capacity (Personal & Resources) | Licensed mech engineer | 5 | Similar experience | 2 | 2022-12-21 | Has experience in water projects but not specificied what roles and task are being done | please put a detailed description about their roles in the project not just the name of the project alone |  |  |  |  | 2
E.2.31 | Capacity (Personal & Resources) | Licensed elec engineer | 0 | Availability and commitment | 3 | 2022-12-21 | Slight concern on the current projects being handled by the EE | [5 empty] | 3
E.2.32 | Capacity (Personal & Resources) | Licensed elec engineer | 10 | Total experience | 3 | 2022-12-21 | Only has 7 years of experience 6 of which are mostly related to water industry | [5 empty] | 3
E.2.33 | Capacity (Personal & Resources) | Licensed elec engineer | 5 | Similar experience | 3 | 2022-12-21 | Meets some of the requirements of the client. However, unable to have experience on 50 MLD Intake and 1000mm Diam works | [5 empty] | 3
E.2.34 | Capacity (Personal & Resources) | A&I engineer | 0 | Availability and commitment | 3 | 2022-12-21 | Avaialability may be a slight concern | [5 empty] | 3
E.2.35 | Capacity (Personal & Resources) | A&I engineer | 10 | Total experience | 5 | 2022-12-21 | Has 42 years of experience in construction and some experience on water industry | [5 empty] | 5
E.2.36 | Capacity (Personal & Resources) | A&I engineer | 5 | Similar experience | 4 | 2022-12-21 | Only has 6 years of experience out of 42. At the same time meets most of the requirements of client | [5 empty] | 4
E.2.37 | Capacity (Personal & Resources) | Construction Manager | 0 | Availability and commitment | 4 | 2022-12-21 | No major projects that may significantly affect availability | [5 empty] | 4
E.2.38 | Capacity (Personal & Resources) | Construction Manager | 10 | Total experience | 4 | 2022-12-21 | has 26 years experience in construction 17 of which are related to water industry | [5 empty] | 4
E.2.39 | Capacity (Personal & Resources) | Construction Manager | 5 | Similar experience | 4 | 2022-12-21 | Most of the projects in water are in conveyance and rehabilitation of pipeline | [5 empty] | 4
E.2.40 | Capacity (Personal & Resources) | Commissioning manager | 0 | Availability and commitment | 2 | 2022-12-21 | Availability is a concern since he is mostly involved in several ongoing projects of their company | [5 empty] | 2
E.2.41 | Capacity (Personal & Resources) | Commissioning manager | 10 | Total experience | 5 | 2022-12-21 | has 34 years of experience 24 of which are related to water industry | [5 empty] | 5
E.2.42 | Capacity (Personal & Resources) | Commissioning manager | 5 | Similar experience | 4 | 2022-12-21 | Some of the requirements are achieved. Most of his experience are in water conveyance | [5 empty] | 4
E.2.43 | Capacity (Personal & Resources) | Procurement manager | 0 | Availability and commitment | 4 | 2022-12-21 | Avaialability is less of a concern | [5 empty] | 4
E.2.44 | Capacity (Personal & Resources) | Procurement manager | 10 | Total experience | 4 | 2022-12-21 | 10 years of experiece as a procurement officer | [5 empty] | 4
E.2.45 | Capacity (Personal & Resources) | Procurement manager | 5 | Similar experience | 5 | 2022-12-21 | Has experience on procurement in water construction projects | [5 empty] | 5
E.2.46 | Capacity (Personal & Resources) | Planner/Scheduler | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is less of a concern | [5 empty] | 4
E.2.47 | Capacity (Personal & Resources) | Planner/Scheduler | 5 | Total experience | 3 | 2022-12-21 | only has 4 years of experience | [5 empty] | 3
E.2.48 | Capacity (Personal & Resources) | Planner/Scheduler | 3 | Similar experience | 5 | 2022-12-21 | Most experience are involved in water industry projects | [5 empty] | 5
E.3 | Certifications on quality, safety and occupational health program | Certifications on quality, safety and occupational health program | 0 | 0
E.3.1 | Certifications on quality, safety and occupational health program |  | 0 | Certification on quality | 4 | 2022-12-21 | Has documents ISO certification for quality management | [5 empty] | 4
E.3.2 | Certifications on quality, safety and occupational health program |  | 0 | Certification on safety | 5 | 2022-12-21 | Has presented certificates of safety and presented key members who practice safety and health | [5 empty] | 5
E.3.3 | Certifications on quality, safety and occupational health program |  | 0 | Certification on OHP | 5 | 2022-12-21 | Has certificated for OHP (ISO certification) | [5 empty] | 5
E.4 | Training plan | Training plan | 0 | 0
E.4.1 | Training plan |  | 0 | Written eviden | 3 | 2022-12-21 | Has documents for implementation of training for the project | [5 empty] | 3
E.4.2 | Training plan |  | 0 | Training plan and schedule | 0 | 2022-12-21 | No provided curriculum or schema showing the line of action for training plans | [5 empty] | 0
E.4.3 | Training plan |  | 0 | Knowledge transfer workshop | 0 | 2022-12-21 | No provided documents pertaining to knowledge transfer workshops | [5 empty] | 0
E.5 | Equipment information | Construction Equipment Information | 0 | 0
E.5.1 | Equipment information |  | 0 | Sourcing | 4 | 2022-12-21 | Provided shedule of equipments needed for their methods in the project | where will you source the equipment, is it inhouse or will be rented? |  |  |  |  | 4
E.5.2 | Equipment information |  | 0 | Efficiency | 0 | 2022-12-21 | Did not show any certificate of operatorship, to equipments, testing of equipments and even quality assurance of equipments | who will be operating the equipment do you certified operators and maintenance? |  |  |  |  | 0
E.5.3 | Equipment information |  | 0 | Availability | 2 | 2022-12-21 | Availability is questionable since because acquisition date are the only data provided | Availability is questionable |  |  |  |  | 2
E.5.4 | Equipment information |  | 0 | Reliability | 0 | 2022-12-21 | Questionable since there are no data provided | who will be operating the equipment do you certified operators and maintenance? |  |  |  |  | 0
E.6 | Construction & Installation Manpower | Construction & Installation Manpower | 0 | 0
E.6.1 | Construction & Installation Manpower |  | 0 | Construction manpower | 4 | 2022-12-21 | Adequate and comparable to other bidders | [5 empty] | 4
E.6.2 | Construction & Installation Manpower |  | 0 | Installation manpower | 4 | 2022-12-21 | Adequate and comparable to other biddrs | [5 empty] | 4

## PrimeBMD
DMCI
ID | Hierachy levels |  |  |  | First Time Assessment |  |  |  | Second Assessment
ID | Level 1 | Level 2 | Level 3 | Level 4 | Score | Score Date | Narrative | Clarification Note | Answer from Bidder | Answered date | Score | Score Date | Final_Score
Total
A | Delivery Plan | 0 | 0 | 0
A.1 | Detailed WBS with schedule and S-curve | 0 | 0 | 0
A.1.1 | Detailed WBS with schedule and S-curve | 0 | 0 | Bidder to follow the WBS defined in ER
A.1.2 | Detailed WBS with schedule and S-curve | 0 | 0 | Sufficiency and completeness of the WBS
A.1.3 | Detailed WBS with schedule and S-curve | 0 | 0 | Schedule is given in required format
A.1.4 | Detailed WBS with schedule and S-curve | 0 | 0 | Interim milestones
A.1.5 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of milestones
A.1.6 | Detailed WBS with schedule and S-curve | 0 | 0 | Clear demonstration of linkages
A.1.7 | Detailed WBS with schedule and S-curve | 0 | 0 | Consistency with delivery narrative and methodological approach
A.1.8 | Detailed WBS with schedule and S-curve | 0 | 0 | Critical path is highlighted in the schedule program
A.1.9 | Detailed WBS with schedule and S-curve | 0 | 0 | Resources allocation
A.1.10 | Detailed WBS with schedule and S-curve | 0 | 0 | S-curve is probably drawn in the schedule program
A.2 | Delivery Narrative | 0 | 0 | 0
A.2.1 | Delivery Narrative | 0 | 0 | Understanding of the works
A.2.2 | Delivery Narrative | 0 | 0 | Well written and demonstration of approach and delivery of the project
A.2.3 | Delivery Narrative | 0 | 0 | Key activities and deliverables
A.2.4 | Delivery Narrative | 0 | 0 | Feasibility of the approach
A.2.5 | Delivery Narrative | 0 | 0 | Constraints involved with the approach
A.2.6 | Delivery Narrative | 0 | 0 | Resources allocation are persuative and feasible
A.2.7 | Delivery Narrative | 0 | 0 | Advantage of offerred contract strategy
A.2.8 | Delivery Narrative | 0 | 0 | Linkage to deliverable plan (above)
A.2.9 | Delivery Narrative | 0 | 0 | Added value to the Client
A.3 | Safety Plan | 0 | 0 | 0
A.3.1 | Safety Plan | 0 | 0 | Overall Safety Plan
A.3.2 | Safety Plan | 0 | 0 | Safety personnel
A.3.3 | Safety Plan | 0 | 0 | Safety plan for each WP, particularly for critical work items
A.3.4 | Safety Plan | 0 | 0 | Demonstration of historical records, data on safety of previous projects
A.3.5 | Safety Plan | 0 | 0 | Safety compliance to Client's requirement
A.3.6 | Safety Plan | 0 | 0 | Safety compliance to local authority
A.3.7 | Safety Plan | 0 | 0 | Evacuation and immediate actions to follow when safety incident occurs
A.4 | Risk Management Plan (including contingency plan) | 0 | 0 | 0
A.4.1 | Risk Management Plan (including contingency plan) | 0 | 0 | Overall risk management plan
A.4.2 | Risk Management Plan (including contingency plan) | 0 | 0 | Specific risk plan for critical work
A.4.3 | Risk Management Plan (including contingency plan) | 0 | 0 | Understanding risks, particularly during execution on critical items
A.4.4 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk assessment methodology
A.4.5 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk management register and tool
A.4.6 | Risk Management Plan (including contingency plan) | 0 | 0 | Risk removal, reduction, and mitigation plan
A.4.7 | Risk Management Plan (including contingency plan) | 0 | 0 | Feasibility of the overal risk plan
A.5 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | 0
A.5.1 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Completeness of deliverables in tabular format
A.5.2 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Linkage of deliverables to detailed schedule
A.5.3 | Detailed list of deliverables with submission/completion timeline for each work package or item. | 0 | 0 | Feasibility of the deliverable plan
B | Design | 0 | 0 | 0
B.1 | 0 | M&E | 0 | 0
B.1.1 | Design | M&E | General | QA/QC
B.1.2 | Design | M&E | General | Deliverable Plan
B.1.3 | Design | M&E | General | Value Engineering
B.1.4 | Design | M&E | General | Resource Plan
B.1.5 | Design | M&E | General | Risk and safety in design
B.1.6 | Design | M&E | Intake Chamber | Feasibility
B.1.7 | Design | M&E | Intake Chamber | Constructability
B.1.8 | Design | M&E | Intake Chamber | Correctness
B.1.9 | Design | M&E | Outside Intake Chamber | Feasibility
B.1.10 | Design | M&E | Outside Intake Chamber | Constructability
B.1.11 | Design | M&E | Outside Intake Chamber | Correctness
B.2 | 0 | Automation and Instrumentation (A&I) | 0 | 0
B.2.1 | Design | Automation and Instrumentation (A&I) | General | QA/QC | 3 | [7 empty] | 3
B.2.2 | Design | Automation and Instrumentation (A&I) | General | Deliverable Plan
B.2.3 | Design | Automation and Instrumentation (A&I) | General | Value Engineering
B.2.4 | Design | Automation and Instrumentation (A&I) | General | Resource Plan
B.2.5 | Design | Automation and Instrumentation (A&I) | General | Risk and safety in design
B.2.6 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Feasibility
B.2.7 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Constructability
B.2.8 | Design | Automation and Instrumentation (A&I) | Intake Chamber | Correctness
B.2.9 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Feasibility
B.2.10 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Constructability
B.2.11 | Design | Automation and Instrumentation (A&I) | Outside Intake Chamber | Correctness
B.3 | 0 | Hydraulics and others | 0 | 0
B.3.1 | Design | Hydraulics and others | General | QA/QC
B.3.2 | Design | Hydraulics and others | General | Deliverable Plan
B.3.3 | Design | Hydraulics and others | General | Value Engineering
B.3.4 | Design | Hydraulics and others | General | Resource Plan
B.3.5 | Design | Hydraulics and others | General | Risk and safety in design
B.3.6 | Design | Hydraulics and others | Intake Chamber | Feasibility
B.3.7 | Design | Hydraulics and others | Intake Chamber | Constructability
B.3.8 | Design | Hydraulics and others | Intake Chamber | Correctness
B.3.9 | Design | Hydraulics and others | Outside Intake Chamber | Feasibility
B.3.10 | Design | Hydraulics and others | Outside Intake Chamber | Constructability
B.3.11 | Design | Hydraulics and others | Outside Intake Chamber | Correctness
B.4 | 0 | Civil/structural design | 0 | 0
B.4.1 | Design | Civil/structural design | General | QA/QC
B.4.2 | Design | 0 | General | Deliverable Plan
B.4.3 | Design | 0 | General | Value Engineering
B.4.4 | Design | 0 | General | Resource Plan
B.4.5 | Design | 0 | General | Risk and safety in design
B.4.6 | Design | 0 | Intake Chamber | Feasibility
B.4.7 | Design | 0 | Intake Chamber | Constructability
B.4.8 | Design | 0 | Intake Chamber | Correctness
B.4.9 | Design | 0 | Outside Intake Chamber | Feasibility
B.4.10 | Design | 0 | Outside Intake Chamber | Constructability
B.4.11 | Design | 0 | Outside Intake Chamber | Correctness
C | Construction/Installation Program and methodology | 0 | 0 | 0
C.1 | 0 | Control System, Automation & Instrumentation | 0 | 0
C.1.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.1.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.1.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.1.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.1.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.2 | 0 | Main Mechanical Works | 0 | 0
C.2.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.2.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.2.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.2.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.2.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.3 | 0 | Main Electrical Works | 0 | 0
C.3.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.3.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.3.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.3.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.3.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.4 | 0 | Piping | 0 | 0
C.4.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.4.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.4.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.4.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.4.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
C.5 | 0 | Other civil Structure | 0 | 0
C.5.1 | Construction/Installation Program and methodology |  | Asset information | Efficiency
C.5.2 | Construction/Installation Program and methodology |  | Asset information | Sourcing
C.5.3 | Construction/Installation Program and methodology |  | Methodology | Overal installation methodology
C.5.4 | Construction/Installation Program and methodology |  | Methodology | Demontration of clear narrative description of methodology/Deliverable plan
C.5.5 | Construction/Installation Program and methodology |  | Methodology | Feasibility of methodology
D | Procurement and Installation of long-lead equipment and major process items | Procurement and Installation of long-lead equipment and major process items | 0 | 0
D.1 | 0 | Procurement plan and list of sub-work packages | 0 | 0
D.1.1 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Details of proposed procurement plan
D.1.2 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Supplier detail
D.1.3 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Installation and testing
D.1.4 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Warantty and defect liability
D.1.5 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Feasibility of procurement methodology
D.1.6 | Procurement and Installation of long-lead equipment and major process items | 0 | 0 | Added value to the Client
D.2 | 0 | Delivery, storage, logistics and materials management plan. | 0 | 0
D.2.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Storage plan on site
D.2.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Losgistic plan
D.3 | 0 | Equipment list | 0 | 0
D.3.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Testing schedule
D.3.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | FAT
D.3.3 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Feasibility of installation method
D.4 | 0 | Service support | 0 | 0
D.4.1 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Availability of local service support
D.4.2 | Procurement and Installation of long-lead equipment and major process items |  | 0 | Responsibility of local service support
E | Capacity (Personal & Resources) | Capacity (Personal & Resources) | 0 | 0
E.1 | 0 | Organizational chart | 0 | 0
E.1.1 | Capacity (Personal & Resources) |  | 0 | Overal organization chart | 5 | 2022-12-21 | Detailed Org chart is presented | [5 empty] | 5
E.1.2 | Capacity (Personal & Resources) |  | 0 | Functional linkage of the chart | 5 | 2022-12-21 | Logical and Reasonable | [5 empty] | 5
E.2 | 0 | Key team members | 0 | 0
E.2.1 | Capacity (Personal & Resources) | PM | 0 | Availability and commitment | 4 | 2022-12-21 | Availability may be a slight concern since PM currently holds an ongoing bulk water supply project in Davao | [5 empty] | 4
E.2.2 | Capacity (Personal & Resources) | PM | 15 | Total Experience (15 years) | 5 | 2022-12-21 | Has 44 years of experience in construction 33 of which are related to water industry | [5 empty] | 5
E.2.3 | Capacity (Personal & Resources) | PM | 10 | Similar experience (10 years) | 5 | 2022-12-21 | Exceeded requirements of client | [5 empty] | 5
E.2.4 | Capacity (Personal & Resources) | Project Controller | 0 | Availability and commitment | 3 | 2022-12-21 | Holds multiple projects in company affecting availability | [5 empty] | 3
E.2.5 | Capacity (Personal & Resources) | Project Controller | 10 | Total Experience of the PM (10 years) | 4 | 2022-12-21 | Has 17 years of experience in construction most of which are related to water | [5 empty] | 4
E.2.6 | Capacity (Personal & Resources) | Project Controller | 5 | Similar experience of the PM (5 years) | 5 | 2022-12-21 | 90%-95% achieved the requirements of Manila Water when it comes to project Management | [5 empty] | 5
E.2.7 | Capacity (Personal & Resources) | Safety Manager | 0 | Availability and commitment | 3 | 2022-12-21 | Availability may be a slight concern since he currently holds a big water project | [5 empty] | 3
E.2.8 | Capacity (Personal & Resources) | Safety Manager | 5 | Total Experience of the PM (10 years) | 5 | 2022-12-21 | 27 years of experience in construction most of which are related to water | [5 empty] | 5
E.2.9 | Capacity (Personal & Resources) | Safety Manager | 3 | Similar experience of the PM (5 years) | 5 | 2022-12-21 | exceeded requirements of t client when it comes to safety manager. | [5 empty] | 5
E.2.10 | Capacity (Personal & Resources) | Contract Administrator | 0 | Availability and commitment | 3 | 2022-12-21 | Availability may be a slight concern since he currently holds a big water project | [5 empty] | 3
E.2.11 | Capacity (Personal & Resources) | Contract Administrator | 10 | Total experience | 5 | 2022-12-21 | 26 years of experience in construction most of which are related to water | [5 empty] | 5
E.2.12 | Capacity (Personal & Resources) | Contract Administrator | 5 | Similar experience | 5 | 2022-12-21 | exceeded requirements of t client when it comes to safety manager. | [5 empty] | 5
E.2.13 | Capacity (Personal & Resources) | Admin assistant Staff | 0 | Availability and commitment | 4 | 2022-12-21 | Availability is less of a concern | [5 empty] | 4
E.2.14 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Total experience | 5 | 2022-12-21 | 18 years of experience as an admin assistant | [5 empty] | 5
E.2.15 | Capacity (Personal & Resources) | Admin assistant Staff | 5 | Similar experience | 4 | 2022-12-21 | 5 years experience in big water projects | [5 empty] | 4
E.2.16 | Capacity (Personal & Resources) | Quality manager | 0 | Availability and commitment | 3 | 2022-12-21 | Holds two (2) big projects that may affect availability | [5 empty] | 3
E.2.17 | Capacity (Personal & Resources) | Quality manager | 10 | Total experience | 5 | 2022-12-21 | Has 13 years of total experience in construction most of which are relate to water construction | [5 empty] | 5
E.2.18 | Capacity (Personal & Resources) | Quality manager | 5 | Similar experience | 5 | 2022-12-21 | exceeded requirements of client in terms of quality manager position | [5 empty] | 5
E.2.19 | Capacity (Personal & Resources) | Design manager | 0 | Availability and commitment | 3 | 2022-12-21 | Availability may be a concern, design manager is involved in a big water project | [5 empty] | 3
E.2.20 | Capacity (Personal & Resources) | Design manager | 10 | Total experience | 5 | 2022-12-21 | Has 18 years of experience all related to water construction | [5 empty] | 5
E.2.21 | Capacity (Personal & Resources) | Design manager | 5 | Similar experience | 5 | 2022-12-21 | Exceeded requiremets of client in design manager | [5 empty] | 5
E.2.22 | Capacity (Personal & Resources) | Licensed structural engineer | 0 | Availability and commitment | 2 | 2022-12-21 | Availability may be a concern, structural engr. Acts as a consultant | [5 empty] | 2
E.2.23 | Capacity (Personal & Resources) | Licensed structural engineer | 10 | Total experience | 5 | 2022-12-21 | 47 years of experience in water construction | [5 empty] | 5
E.2.24 | Capacity (Personal & Resources) | Licensed structural engineer | 5 | Similar experience | 4 | 2022-12-21 | Met minimum requirements for structural engr. Focused on WTP Design and build | [5 empty] | 4
E.2.25 | Capacity (Personal & Resources) | Hydraulic engineer | 0 | Availability and commitment | 2 | 2022-12-21 | Availability may be a concern,hydraulics engr. Acts as a consultant | [5 empty] | 2
E.2.26 | Capacity (Personal & Resources) | Hydraulic engineer | 10 | Total experience | 5 | 2022-12-21 | Has 43 years of construction experience 40 of which are related to large sacle water projects | [5 empty] | 5
E.2.27 | Capacity (Personal & Resources) | Hydraulic engineer | 5 | Similar experience | 5 | 2022-12-21 | Exceeded requirements of client | [5 empty] | 5
E.2.28 | Capacity (Personal & Resources) | Licensed mech engineer | 0 | Availability and commitment | 2 | 2022-12-21 | Availability may be a concern,mech engr. Acts as a consultant | [5 empty] | 2
E.2.29 | Capacity (Personal & Resources) | Licensed mech engineer | 10 | Total experience | 5 | 2022-12-21 | has 31 years of experience in construction 28 of which are related to water | [5 empty] | 5
E.2.30 | Capacity (Personal & Resources) | Licensed mech engineer | 5 | Similar experience | 5 | 2022-12-21 | achieved requirements of client | [5 empty] | 5
E.2.31 | Capacity (Personal & Resources) | Licensed elec engineer | 0 | Availability and commitment | 2 | 2022-12-21 | Availability may be a concern,elec. engr. Acts as a consultant | [5 empty] | 2
E.2.32 | Capacity (Personal & Resources) | Licensed elec engineer | 10 | Total experience | 5 | 2022-12-21 | Has 43 years of experience in water construction industry | [5 empty] | 5
E.2.33 | Capacity (Personal & Resources) | Licensed elec engineer | 5 | Similar experience | 5 | 2022-12-21 | Exceeded requirements of client | [5 empty] | 5
E.2.34 | Capacity (Personal & Resources) | A&I engineer | 0 | Availability and commitment | 1 | 2022-12-21 | Has multiple (more than 5) projects ongoing which may affect availability | [5 empty] | 1
E.2.35 | Capacity (Personal & Resources) | A&I engineer | 10 | Total experience | 4 | 2022-12-21 | Has 24 years of experience in construction industry | [5 empty] | 4
E.2.36 | Capacity (Personal & Resources) | A&I engineer | 5 | Similar experience | 3 | 2022-12-21 | Almost achieved the requirements of client for A&I ENGINEER | [5 empty] | 3
E.2.37 | Capacity (Personal & Resources) | Construction Manager | 0 | Availability and commitment | 3 | 2022-12-21 | Has projects that are almost finished which may affect availability | [5 empty] | 3
E.2.38 | Capacity (Personal & Resources) | Construction Manager | 10 | Total experience | 5 | 2022-12-21 | 28 years of experience in the construction industry 20 of which are in water | [5 empty] | 5
E.2.39 | Capacity (Personal & Resources) | Construction Manager | 5 | Similar experience | 4 | 2022-12-21 | Almost achieved the requirements of client for Construction manager | [5 empty] | 4
E.2.40 | Capacity (Personal & Resources) | Commissioning manager | 0 | Availability and commitment | 2 | 2022-12-21 | Has two (2) major projects currently ongoing that might affect availability | [5 empty] | 2
E.2.41 | Capacity (Personal & Resources) | Commissioning manager | 10 | Total experience | 5 | 2022-12-21 | has 13 years of straight experience in water industry construction | [5 empty] | 5
E.2.42 | Capacity (Personal & Resources) | Commissioning manager | 5 | Similar experience | 5 | 2022-12-21 | Exceeded requirements of client | [5 empty] | 5
E.2.43 | Capacity (Personal & Resources) | Procurement manager | 0 | Availability and commitment | 4 | 2022-12-21 | Availability may be a slight concern | [5 empty] | 4
E.2.44 | Capacity (Personal & Resources) | Procurement manager | 10 | Total experience | 5 | 2022-12-21 | Has 22 years of experience most of which are related to water industry | [5 empty] | 5
E.2.45 | Capacity (Personal & Resources) | Procurement manager | 5 | Similar experience | 5 | 2022-12-21 | exceeded requirement of Manila water similar to other employees | [5 empty] | 5
E.2.46 | Capacity (Personal & Resources) | Planner/Scheduler | 0 | Availability and commitment | 4 | 2022-12-21 | Availability may be a slight concern. Currently involved in two major projects | [5 empty] | 4
E.2.47 | Capacity (Personal & Resources) | Planner/Scheduler | 5 | Total experience | 5 | 2022-12-21 | 12 years of experience in construction 10 of which are related to water | [5 empty] | 5
E.2.48 | Capacity (Personal & Resources) | Planner/Scheduler | 3 | Similar experience | 5 | 2022-12-21 | Exceeded requirements of client for planner and scheduler | [5 empty] | 5
E.3 | Certifications on quality, safety and occupational health program | Certifications on quality, safety and occupational health program | 0 | 0
E.3.1 | Certifications on quality, safety and occupational health program |  | 0 | Certification on quality | 5 | 2022-12-21 | Has adequate documentation and certificates for quality management | [5 empty] | 5
E.3.2 | Certifications on quality, safety and occupational health program |  | 0 | Certification on safety | 5 | 2022-12-21 | Has certification documents for safety at the same time multiple key members are safety and health practitioners | [5 empty] | 5
E.3.3 | Certifications on quality, safety and occupational health program |  | 0 | Certification on OHP | 5 | 2022-12-21 | Has certification documents for OHP | [5 empty] | 5
E.4 | Training plan | Training plan | 0 | 0
E.4.1 | Training plan |  | 0 | Written eviden | 5 | 2022-12-21 | Has provided documents of training plan for the project which include multiple aspects from safety, to environmental and hands on training | [5 empty] | 5
E.4.2 | Training plan |  | 0 | Training plan and schedule | 3 | 2022-12-21 | Curriculum and Schema are provided but not in detail | [5 empty] | 3
E.4.3 | Training plan |  | 0 | Knowledge transfer workshop | 4 | 2022-12-21 | Provided enough trainings related to knowledge transfer | [5 empty] | 4
E.5 | Equipment information | Construction Equipment Information | 0 | 0
E.5.1 | Equipment information |  | 0 | Sourcing | 2 | 2022-12-21 | Detailed information on the equipment schedule are not provided | [5 empty] | 2
E.5.2 | Equipment information |  | 0 | Efficiency | 5 | 2022-12-21 | Provided Certificates of operation and inspection of equipments | [5 empty] | 5
E.5.3 | Equipment information |  | 0 | Availability | 5 | 2022-12-21 | Provided documents for availability of equipment | [5 empty] | 5
E.5.4 | Equipment information |  | 0 | Reliability | 5 | 2022-12-21 | Has passed inspection requirements | [5 empty] | 5
E.6 | Construction & Installation Manpower | Construction & Installation Manpower | 0 | 0
E.6.1 | Construction & Installation Manpower |  | 0 | Construction manpower | 5 | 2022-12-21 | Complete and has advantage in competitors in terms of manpower distribution | [5 empty] | 5
E.6.2 | Construction & Installation Manpower |  | 0 | Installation manpower | 5 | 2022-12-21 | Every team has a specific role and installers are in adequate number | [5 empty] | 5

## Definition
Score Definition
Per discipline
Score | Definition | Scale | Pass or Fail
0 | No-compliance, incomplete, insufficient | [0-1] | No-compliance, incomplete, insufficient
1 | Complete/responsive/poor quality and poor standard | [1-2) | Partial complete/partial responsive/very poor quality and poor standard
2 | Average quality | [2-3) | Average quality
3 | Good quality, address key criteria, key risks and level of complexity | [3-4) | Good quality, address key criteria, key risks and level of complexity
4 | Very good quality, clear valuate to Client | [4-5) | Very good quality, clear valuate to Client
5 | Outstanding, exceed expection, exceptional value to Client | 5 | Outstanding, exceed expectation, exceptional value to Client

## Evaluators
Instruction to Evaluators
1 | Instructors read respective sections of Bidder's technical proposal carefully
2 | Give Bidder score in the range from 1 to 5 per "Definition" tab --> Note that Evaluators can also define the meaning of scores from 1 -5 in their own engineering judment.
3 | Evaluators do not insert or merge any row in the evaluation tab --> this will create problems for later compilation as each row has its unique ID.
4 | Evaluators MUST provide narrative on how they give score, if not provide narrative, the score will be considered invalid and Evaluators will have to do the work again.
| Evaluators Matrix | [28 empty] | Evaluators ID | Evaluator Name | Discipline | Company
[5 empty] | Arcadis | [18 empty] | Manila Water
|  | Main section | Subsection | Name | Nam | Philip | Irish | William | Arnold | Kim | Rowena | Mun | Mark | Clyde | Josua | Riker | Paul | Jason | Eriz | Jo-Anna | James | Vincent |  | 7 | 8 | 9 | 10 | 11 | 12 | 1 | Nam Le | PM and overall | Arcadis
|  | A | A.1 | Detailed WBS with schedule and S-curve | x | x |  |  | x | x | x | [11 empty] | 5 | x | x |  |  |  |  | 2 | Philip Balingit | PM and overall | Arcadis
|  |  | A.2 | Delivery Narrative | x | x |  |  | x | x | x | [11 empty] | 5 | x | x |  |  |  |  | 3 | Raymund Siana | Mechanical | Arcadis
|  |  | A.3 | Safety Plan | x | x |  |  | x | x | x | [11 empty] | 5 | x | x |  |  |  |  | 4 | Jason Pablo | Hydraulic | Arcadis
|  |  | A.4 | Risk Management Plan (including contingency plan) | x | x |  |  | x | x | x | [11 empty] | 5 | x | x |  |  |  |  | 5 | Jo-Anna | Electrical | Arcadis
|  |  | A.5 | Detailed list of deliverables with submission/completion timeline for each work package or item. | x | x |  |  | x | x | x | [11 empty] | 5 | x | x |  |  |  |  | 6 | Mark Ogot | Civil and Structural | Arcadis
|  | B | B.1 | M&E | x | x |  |  | x |  |  | x | [7 empty] | x | x | x | 7 | [6 empty] | 7 | William Davin Perez | Section 5
|  |  | B.2 | Automation and Instrumentation (A&I) | x | x | [5 empty] | x | [7 empty] | x | x | x | 6 | [6 empty] | 8 | Rowena Gonzles
|  |  | B.3 | Hydraulics and others | x | x |  |  |  | x | x | [6 empty] | x |  |  |  |  | 5 | [6 empty] | 9 | Kim
|  |  | B.4 | Civil/structural design | x | x | [6 empty] | x | x | x | [7 empty] | 5 | [6 empty] | 10 | Riker
|  | C | C.1 | Control System, Automation & Instrumentation | x | x | [5 empty] | x | [7 empty] | x | x | x | 6 | [6 empty] | 11 | Arnold
|  |  | C.2 | Main Mechanical Works | x | x | [5 empty] | x | [7 empty] | x | x | x | 6 | [6 empty] | 12 | Paul
|  |  | C.3 | Main Electrical Works | x | x |  |  | x |  |  | x | [7 empty] | x | x | x | 7 | [6 empty] | 13 | Irish | Section 5
|  |  | C.4 | Piping | x | x |  |  |  | x | x | x |  | x | x |  |  | x |  | x | x | x | 11 | [6 empty] | 14 | Clyde
|  |  | C.5 | Other civil Structure | x | x | [7 empty] | x | x | [7 empty] | 4
|  | D | D.1 | Procurement plan and list of sub-work packages | x | x |  |  |  | x | x |  |  |  |  | x | [6 empty] | 5 | x | x
|  |  | D.2 | Delivery, storage, logistics and materials management plan. | x | x |  |  |  | x | x |  |  |  |  | x | [6 empty] | 5 | x | x | [5 empty] | Byder Nangit | PM and overall
|  |  | D.3 | Equipment list | x | x |  |  |  | x | x | x |  |  |  | x |  |  |  | x | x | x | 9 | x | x | [5 empty] | Rodel Javier | PM and overall
|  | E | E.1 | Organizational chart | x | x | x | x | [14 empty] | 4 | x | x | [5 empty] | Jhaspher Laya
|  |  | E.2 | Key team members | x | x | x | x | [14 empty] | 4 | x | x
|  |  | E.3 | Certifications on quality, safety and occupational health program | x | x | x | x | [14 empty] | 4 | x | x
|  |  | E.4 | Training plan | x | x | x | x | [14 empty] | 4 | x | x
|  |  | E.5 | Construction Equipment Information | x | x | x | x | [14 empty] | 4 | x | x
|  |  | E.6 | Construction & Installation Manpower | x | x | x | x | [14 empty] | 4 | x | x
|  |  |  | Coffee and Donuts | [12 empty] | XXX | [5 empty] | 1